## 2022-4 Action Plan
HREiR Action plan template (2022-2025)
| Details |  |  |  |  | The institutional audience* for this action plan includes (only include direct beneficiaries; complete or delete, as appropriate):
| Institution name: | University of Westminster |  |  |  | Institutional Audience
| Cohort number: | 13 |  |  |  | Audience (direct beneficiaries of the action plan) |  | Number of | Comments
| Date of submission: | 2022-08-04 |  |  |  | Research staff |  | 68
| Institutional context: | University of Westminster (UoW) is a post-92 institution based on four campuses across London, it is organised into three colleges of four schools in each. The University currently employs 68 colleagues on research-only contracts as part of a broader academic body of 924 and our research strengths fall into four key areas – sustainable living, healthy society, inclusive society and creative communities. Research and Knowledge Exchange is supported across the institution by the Research & Knowledge Exchange Office (RKEO), who have expanded from 9 to 20 colleagues in the last three years. |  |  |  | Postgraduate researchers |  | x
[6 empty] | Research and teaching staff |  | 924
[6 empty] | Teaching-only staff |  | x
[6 empty] | Technicians |  | x
[6 empty] | Clinicians |  | x
[6 empty] | Professional support staff |  | x
[6 empty] | Other (please provide numbers and details): |  | x
HR EiRA Action Plan | [7 empty] | For future progress reporting
| Obligation | Action | Carried over from previous action plan? | Deadline | Responsibility | The targeted impact of the action (success measure) | Comments (optional) | Progress update | The actual impact of the action (reporting against the success measure) | Outcome (ongoing/carried forward/no further action)
Environment and Culture
Awareness and engagement
The aims of these obligations are to work towards an open and inclusive research culture, and to ensure broad understanding and awareness of this amongst researchers.
ECI1 | Ensure all relevant staff are aware of the Concordat. | (Carried Forward) - Incorporate the Concordat in induction materials - Draw attention to the Concordat at relevant RDP sessions (New) - Draw attention to the Concordat through our Researcher Development Hub - Incorporate the Concordat, where appropriate, in any recorded materials for researchers - Make the Concordat a core part of the Researcher Development Awards initiative | Y | 2025-08-01 | RKEO | - At least 50% of research-only staff to respond to the relevant CEDARS question (42.1) as having an understanding of the Concordat to Support the Career Development of Researchers in the 2025 CEDARS. | - This action is, in part, carried over from our previous plan and the success measure remains the same. - The success measure was marginally missed in the last CEDARS (46% of res-only staff, but 52% of researcher-plus staff) and we hope that the new parts of this action wiill see this figure increase.
ECI2 | Ensure institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers. | (Carried Forward) - RDWG to retain a line of communication with EDI Committee - Continue to review internal and external webpages - Use the RKEO blog as a platform to communicate inclusive, equitable and transparent policies - Communicate policies and practices as appropriate through the RKEO newsletter (New) - Regular meetings to be held between RKEO and the new OD team - Regular meetings to be held between RKEO and the University's new EDI officer - RKEO to filter important information and opportunities to school/community/network level channels to broaden engagement - Newsletter engagement (clicks on links) to increase by 50% | Y | Aug-23; Aug-25 | RKEO, OD Team | - A mean average of 65% of researcher plus staff responding to CEDARS qu. 13 (agreement that the institution treats you fairly in relation to…) to agree they are treated fairly in 2025. - An increased online presence. Our RKEO twitter account aims to have 1000 followers bu Aug '23. | - This action is, in part, carried over from our previous plan and the success measure remains the same. - The success measure was missed in the last CEDARS, but had a 2024 deadline for completion. - The UoW RKEO Twitter account currently has 815 followers and the mean average response to Q.13 of CEDARS in 2021 was 55% - The RKEO mailing list now has over 1100 subscribers, and engagement with the newsletter (number of people following links) has grown by 5% in the last year. - We also now have a separate maililng list of 120+ early-career researchers, who receive targeted comms approved by institutional ECR reps. - Our internal and external webpages have been improved since our last action plan, with the redesign of our blog, implementation of the Res Dev Hub, and updates to our internal SP Comms site. These pages are all monitored, reviewed and updated by RKEO. - The RDWG has expanded its membership in the last two years to include a rep from each of the University's four staff networks which feed into EDI Committe (the Q+ [LGBTQI+] network, the BME network, Disability network, and the Women of Westminster network)
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and using the outcomes to improve institutional practices. | (Carried Forward) '- The RDWG will continue to meet once per semester to monitor the quality of the research environment and culture. - Continue to seek feedback on research culture at RDP sessions. - Continue to engage with the CEDAR survey at every opportunity (New) - Seek (and report on) more feedback on our research environment and culture through the new ECR network and through planned work of the Readers' and Professors' representatives. - Seek (and report on) feedback from recipients of RDAs at their cohort meetings. | Y | Aug-24; Aug-25 | RKEO, ECR Reps | - 70% of all researcher plus respondents to CEDARS claiming to feel valued at work. - By 2024, we hope that the ECR network will have established a regular mechanism for gaining insight into the consituency's experiences of the research environment at UoW. - By Aug '25, we hope that this feedback, combined with CEDARS data, can systematically inform Research Committee work around research environment, beginning with an annual report. | - This action is, in part, carried over from our previous plan and the success measure remains the same. - 62% of respondents in the last CEDARS felt valued at work at the last time of asking - RDP attendees have been reluctant to give open feedback on E&C. We hope that the new parts of this action will see us meet our success measure.
ECR1 | Encourage researchers to actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students. | (Carried Forward) - The need to support newer colleagues in this regard should be addressed by ECR representation on both research committee and in our RDWG. - Training focussed on strengthening upwards and downwards working relationships (Managing Research Relationships from VOX Coaching) will contribute to this end. - RKEO to encourage engagement with our staff networks by disseminating EDI group actions and events to researchers through the RKEO newsletter and online channels. (New) - Encourage more cross-disciplinary/cross-school networking and communication through the ECR network and through renewed focus in the research communities - The RDWG's annual report to Court of Governors should include a narrative of collaboration across schools | Y | 2024-08-01 | RKEO, ECR reps | - 70% of researcher plus respondents to CEDARS to state that they feel valued at work - A welcoming, healthy, supportive research culture. | - This action is, in part, carried over from our previous plan and the success measure remains the same - 62% of staff said they felt valued at work in the last CEDAR survey; a figure that we hope will increase as a result of our continued work in this area. - The RKEO feeds into the annual institutional EDI action plan and are becoming increasingly involved in conversations pertaining to cross-school/college work, for instance in the strategising of our research communities. Workshops co-ordinated by the RKEO this year to encourage discussion around research culture included a session for Readers and Professors to contribute to the updating of our institutional Research & KE strategy, and a session inviting repsonses from across the university to UKRI's draft EDI strategy, allowing a range of voices to inform our response to the consultation call.
Wellbeing and mental health
The aims of these obligations are to champion positive wellbeing amongst researchers, both through appropriate training and enabling new ways of working.
ECI3 | Promote good mental health and wellbeing through the effective management of workloads and people. | - Promote, through RKEO channels, relevant workshops and PDRs, the University's new Report and Support platform for reporting bullying and harassment. - Continue to promote, through the above channels, events from our Health Innovation and Wellbeing research community. - Support colleagues to engage in writing retreats and wellbeing focussed development as part of the RDAs. | N | 2025-08-01 | RKEO | - 70% of research-only staff to respond in CEDARS that they are familiar with UoW processes for reporting bullying or harassment and 90% to trust that the institution would handle any such claim fairly. - 70% of researcher plus respondents to CEDARS q.41.4 to agree that UoW actively promotes the importance of good mental health and wellbeing. | - This is a new action for 2022. - In the last CEDARS, 63% of respondents said they are familiar with our processes for reporting bullying and harassment and 88% believed that the institution would investigate a report fairly. 66% agreed that the University promotes good mental health and wellbeing. There is a significant focus on this in our institutional strategy, 'Being Westminster'.
ECI4 | Ensure managers of researchers are effectively trained in relation to wellbeing and mental health. | - RKEO and RDWG to work with OD team to ensure continually reviewed training for managers meets these needs. - RDWG and RKEO to continue supporting the DI Community; helping with planning and facilitation of events where needed. - Through the Readers' and Professors' representatives, target managers of researchers with email updates around relevant training in this area, and about workshops pertaining to EDI more broadly. | N | Aug-23; Aug-25 | RKEO, RDWG, OD Team | - 85% of researcher plus respondents in CEDARS agreeing that the institution is committed to equality and diversity. - Establish a mailing list with the institution's Readers' and Professors' representatives to allow for more targeted communication of opportunities - By Aug '23, mechanisms should be in place to identify managers of researchers, by Aug '24, training should be rolled out as part of the RDP targeted at this group. This training should be reviewed in Aug '25 and annually from then on. | - This is a new action for 2020. - In the last CEDARS, 82% of respondents agreed that the institution is committed to equality and diversity.
ECM3 | Ensure managers promote a healthy working environment that supports researchers' wellbeing and mental health. | - RKEO to work more closely with OD team, feeding in the research culture angle to relevant conversations. - RKEO to highlight any and all emerging resources (be they through our RD Hub, blog, or external) related to health and wellbeing to managers of researchers and to the university's Readers and Professors constituency. | N | 2024-08-01 | RKEO, OD Team | - 90% of managers of researchers to say that they are confident in responding to issues pertaining to health and wellbeing in CEDARS. | - This is a new action for 2022 - In the last CEDARS, 86% of managers of researchers said that they were confident in responding to issues pertaining to health and wellbeing.
ECM4 | Ensure managers consider fully flexible working requests and other appropriate arrangements to support researchers. | (Carried Forward) '- The consequences of the COVID-19 pandemic forced managers into becoming comfortable with flexible working policies. - Colleagues have become well acquainted with hybrid working and are supported by managers well trained in managing their colleagues (through compulsory HR training) - Our institutional response to COVID-19 is monitored and reviewed by our 'Being Safe, Feeling Safe' group, who continue to review the situtation regularly. (New) - Managers of researchers will continue to implement this policy and guidance, which will be communicated through our RD Hub and strong mailing list as appropriate. | Y | Aug-23; Aug-25 | HR, 'Being Safe, Feeling Safe' Group, Managers of researchers | - A more flexible working environment with healthy researcher-line manager relationships. 60% of managers of researcher staff to describe themselves as confident in managing flexible working requests in CEDARS '23, and 70% in CEDARS '25. | - This action is, in part, carried over from our previous plan and the success measure remains the same - The response to this question in the last iteration of CEDARS was 66%. We hope that the consequences of COVID-19 and the new part of this action will increase this number significantly in the next survey.
ECR3 | Ensure researchers take positive action towards maintaining their wellbeing and mental health. | - Promote, through RKEO channels, relevant workshops and PDRs, the University's new Report and Support platform for reporting bullying and harassment. - Continue to promote, through the above channels, events from our Health Innovation and Wellbeing research community. - Support colleagues to engage in writing retreats and wellbeing focussed development as part of the RDAs. | N | 2023-08-01 | RKEO | - 65% of research-only staff to respond in CEDARS in 2023 that they are familiar with UoW processes for reporting bullying or harassment and 85% to trust that the institution would handle any such claim fairly. - 70% of researcher plus respondents to CEDARS q.41.4 to agree that UoW actively promotes the importance of good mental health and wellbeing in 2023. | - This is a new action for 2022. - In the last CEDARS, 63% of respondents said they are familiar with our processes for reporting bullying and harassment and 88% believed that the institution would investigate a report fairly. 66% agreed that the University promotes good mental health and wellbeing. There is a significant focus on this in our institutional strategy, 'Being Westminster'.
Bullying and harassment
The aims of these obligations are to eliminate bullying and harassment in the research system, tackled through progressive policies and secure mechanisms to address incidents.
ECI3 | Promote a healthy working environment through effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues. | - Promote, through RKEO channels, relevant workshops and PDRs, the University's new Report and Support platform for reporting bullying and harassment. - Continue to promote, through the above channels, events from our Health Innovation and Wellbeing research community. - Support colleagues to engage in writing retreats and wellbeing focussed development as part of the RDAs. | N | Aug-23; Aug-25 | RKEO | - 70% of research-only staff to respond in CEDARS that they are familiar with UoW processes for reporting bullying or harassment and 90% to trust that the institution would handle any such claim fairly. - 70% of researcher plus respondents to CEDARS q.41.4 to agree that UoW actively promotes the importance of good mental health and wellbeing. - By Aug '24, we hope to have developed a policy to support E/M-CRs to go on writing retreats. | - This is a new action for 2022. - In the last CEDARS, 63% of respondents said they are familiar with our processes for reporting bullying and harassment and 88% believed that the institution would investigate a report fairly. 66% agreed that the University promotes good mental health and wellbeing. There is a significant focus on this in our institutional strategy, 'Being Westminster'.
ECM3 | Ensure managers encourage reporting and addressing incidents of discrimination, bullying and harassment. | - RKEO to work more closely with OD team, feeding in the research culture angle to relevant conversations. - RKEO to highlight any and all emerging resources (be they through our RD Hub, blog, or external) related to health and wellbeing to managers of researchers and to the university's Readers and Professors constituency. | N | Aug-23; Aug-25 | RKEO, OD Team | - 90% of managers of researchers to say that they are confident in responding to issues pertaining to health and wellbeing in CEDARS '25. - The RDWG annual report to CoG should include a narrative of the R&KE Office's work with the OD team from Aug '23 | - This is a new action for 2022 - In the last CEDARS, 86% of managers of researchers said that they were confident in responding to issues pertaining to health and wellbeing.
ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to discrimination, harassment and bullying. | (Carried Forward) '- We must draw attention to our, 'Diversity and Dignity at Work and Study Policy' through placing it in a researcher specific online space and provide physical copies of it at the 'Welcome to Westminster' induction. - Compulsory online onboarding training covers basic procedures of how to report misconduct of any kind. (New) - All staff to be aware of our new Report and Support system for reporting bullying, harassment and misconduct - This should be included on our Res Dev Hub | Y | Aug 23; Aug-25 | RKEO, HR | - At least 60% of researcher plus respondents in CEDARS '23 to say they are familiar with UoW mechanisms for reporting harassment and bullying, and 70% in CEDARS '25. | - This action is, in part, carried over from our previous plan and the success measure remains the same - 57.5% of respondents in the last CEDARS said they were familiar with mechanisms to report bullying or harassment. Falling just short of our target, this area has been progressed further since the second CEDARS by the rollout of our new report and support platform. This platform is a result of work from our new organisational development team, who this working group will work more closely with going forward.
Equality, diversity and inclusion
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and adopt practices enhancing equality, diversity and inclusion.
ECI4 / ECM1 | Ensure managers undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work. | - RKEO and RDWG to work with OD team to ensure continually reviewed training for managers meets these needs. - RDWG and RKEO to continue supporting the DI Community; helping with planning and facilitation of events where needed. - Through the Readers' and Professors' representatives, target managers of researchers with email updates around relevant training in this area, and about workshops pertaining to EDI more broadly. - Continue to explore the best ways to approach training and development wrt EDI - RKEO to work with the new DI Community lead to engage the community in creating actions on the back of a reason consultation workshop focused on UKRI's draft EDI strategy - RKEO to work with the DI Community and Collaboration Team on forming small focus groups looking at specific research & KE related EDI barriers to collaboration with external partners | N | 2025-08-01 | RKEO, OD Team, Collaboration Team | - 85% of researcher plus respondents in CEDARS agreeing that the institution is committed to equality and diversity. - Establish a mailing list with the institution's Readers' and Professors' representatives to allow for more targeted communication of opportunities - In response to our institution specific additional CEDARS question, at least 80% of researcher plus staff to say that they have an understanding of our Research Communities in Aug '23. - Produce a resource based on current best practice around overcoming research & KE specific EDI barriers and disseminate as appropriate by Jan '24. This resource should be reviewed in Aug '24 and inform a report of recommendations outlined elsewhere in this document, concerning KE and collaboration barriers in Aug '25. | - This is a new action for 2020. - In the last CEDARS, 82% of respondents agreed that the institution is committed to equality and diversity. - 81% of respondents in the last CEDARS had an understanding of our Research Communities and we hope to maintain this figure in the next iteration of the survey.
ECR2 | Ensure researchers act in accordance with employer and funder policies related to equality, diversity and inclusion. | - After the success of its general ethics workshop, the RKEO will start to offer ethics and integrity training in a self-placed online module over the next two years - RKEO to highlight the annual integrity narrative statement through growing online channels | N | Mar-23; Aug 23 | RKEO | - At least six school specific ethics and integrity workshops to have been offered in August '23 (for academic year 23-4) - The launch of an online ethics training module by March '23 - The RDWG should review this module by Aug'23 | - This is a new action for 2022. - 59 colleagues attended our Ethical Considerations workshop last year, exceeding our target. - The Code of Research Good Practice and Annual lntegrity Narrative statement are publicly available and we are working to better highlight them to our researchers
Research Integrity
The aims of these obligations are to ensure managers and researchers are trained in-, aware of- and maintain high standards of research integrity, and are able to report infringements or misconduct.
ECI5 / ECM2 | Ensure researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity and professional conduct. | (Carried Forward) - Continue to promote the Concordat to Support Research Integrity in our Researcher Development Hub and include it in a digital researcher induction pack. - Continue to run our general ethics workshop, 'Ethical Considerations' three times per year (New) - RKEO to work with UREC in exploring opportunities for an online ethics and integrity training module - Highlight and promote the institution's annual integrity narrative statement through our blog and twitter. - Add to the Ethics self-service section of our Researcher Development Hub with at least two new videos. - Update the RKEO external facing webpages to better frame policies, procedures, successes and definitions of good research integrity. - RKEO to continue encouraging optimum engagement with the relevant integrity training and support - The incorporation of the Concordat to Support Research Integrity into researcher induction materials | Y | Aug-23; Aug-25 | RKEO, UREC | - Offer three ethics sessions per year and achieve an attendance of 50 across them. - The Concordat to Support Research Integrity should be integrated into inductions by Aug '23 - At least 30% of researcher plus CEDARS respondents to state that they have an understanding of the Concordat to Support Research Integrity in the 2025 survey | - This action is, in part, carried over from our previous plan and the success measure remains the same. - In the last CEDARS, 16% of respondents had an understanding of the Res Integrity Concordat - 59 colleagues attended an ethics workshop in 2020/1 - Self-service ethics videos on the Res Dev Hub seek to support in this area and provide a platform for further conversation between colleagues from across the University.
ECM3 | Ensure managers report and address incidents of poor research integrity. | - RKEO to work more closely with OD team, feeding in the research culture angle to relevant conversations. - RKEO to highlight any and all emerging resources (be they through our RD Hub, blog, or external) related to health and wellbeing to managers of researchers and to the university's Readers and Professors constituency. | N | 2025-08-01 | RKEO, OD Team | - 90% of managers of researchers to say that they are confident in responding to issues pertaining to health and wellbeing in CEDARS by Aug-25. | - This is a new action for 2022 - In the last CEDARS, 86% of managers of researchers said that they were confident in responding to issues pertaining to health and wellbeing.
ECR2 | Ensure researchers act in accordance with employer and funder policies related to research integrity. | - After the success of its general ethics workshop, the RKEO will start to offer school specific research ethics and integrity training over the next two years - RKEO to highlight the annual integrity narrative statement through growing online channels | N | 2023-12-01 | RKEO | - At least six school specific ethics and integrity workshops to have been offered | - This is a new action for 2022. - 59 colleagues attended our Ethical Considerations workshop last year, exceeding our target. - The Code of Research Good Practice and Annual lntegrity Narrative statement are publicly available and we are working to better highlight them to our researchers
ECR4 | Ensure researchers use available mechanisms to report staff who fail to meet the expected standards of behaviour in relation to research misconduct. | (Carried Forward) - We must draw attention to our, 'Diversity and Dignity at Work and Study Policy' through placing it in a researcher specific online space and provide physical copies of it at the 'Welcome to Westminster' induction. - Compulsory online onboarding training covers basic procedures of how to report misconduct of any kind. (New) - All staff to be aware of our new Report and Support system for reporting bullying, harassment and misconduct - This should be included on our Res Dev Hub | Y | 2025-08-01 | RKEO | - At least 60% of researcher plus respondents in CEDARS '25 to say they are familiar with UoW mechanisms for reporting harassment and bullying. | - This action is, in part, carried over from our previous plan and the success measure remains the same - 57.5% of respondents in the last CEDARS said they were familiar with mechanisms to report bullying or harassment. Falling just short of our target, this area has been progressed further since the second CEDARS by the rollout of our new report and support platform. This platform is a result of work from our new organisational development team, who this working group will work more closely with going forward.
Policy development
The aims of these obligations are to encourage all researchers to actively contribute to the development of policies driving positive change at their institution.
EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making. | (Carried Forward) - Monitor the effectiveness of the number of research staff on both research committee and the RDWG. Evaluate the impact of this level of representation and increase if necessary. If there is the demand to contribute to these groups, we could perhaps consider rotating representation annually. (New) - Continue to hold consultation workshops, inviting researchers from across the university, to discuss prominent changes to internal and external initiatives or policies. | Y | 2023-12-01 | RKEO, RDWG, OD Team | - Monitor and evaluate the participation of research only staff on decision making bodies annualy with a view to maintaining an appropriate level of representation each year. - Growing attendance at consultation workshops going forward | - This action is, in part, carried over from our previous plan. The success measure has been expanded to include tracking of engagement at consultation workshops. - Through holding more consultation workshops around prominent changes to external and internal policies and initiatives, we hope to best embody this concordat priniple and measure engagement through attendance figures.
ECM5 | Encourage managers to engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution. | - RKEO to continue supporting the growing E-MCR network - RKEO to support Readers and Profs representatives in building their network - RKEO to facilitate further consultation workshops, like the recent session held calling for thougths on the UKRI draft EDI strategy, or on the next REF, or planned sessions calling for thoughts on new internal policy - The incorporation of E/M-CR and Readers/Profs network into induction processes for researchers | N | Dec-23; Aug-24 | RKEO, ECR reps | - Continuing to grow a culture of consultation and input from across the institution. - ECR network to hold its first event by Dec-23 and each of the two constituencies mentioned to be consulted in the process of designing our next Research & KE strategy - By Aug '24, both of these networks should be a part of researchers' induction process | This is a new action for 2022. We relied too heavily on stats from CEDARS in attempting to measure success in this area in our last action plan and feel that committing to event holding and consultation is a clearer indication of steps made towards a more positive research culture which values the thougths of its researchers.
EM5 | Engage with opportunities to contribute to relevant policy development within their institution. | (Carried Forward) - The RKEO mailing list, newsletter and increased online presence will make managers of researchers aware of their various opportunities to contribute to relevant policy. We hope that this will lead to an increase in those beginning to do so alongside manager representation on working groups and Research Committee. (New) - As mentioned elsewhere in this document, encourage engagement from across the university in policy development conversations through consultation workshops and calls for consultation on major pieces of policy, for instance on our new Research & KE Strategy. RDWG to lobby for this as appropriate. | Y | Dec-23; Aug-24 | RKEO, RDWG | - Monitoring and an annural review of committee and working group membership to ensure research managers from all colleges have a fair opportunity to contribute to relevant policy. - At least 55% of researcher plus respondents to CEDARS who manage research staff to state that the institution values their contribution to policy relevant to researchers (question 15.7) - By Dec '23, the E/M-CR and Reader/Prof networks will be holding termly meetings, facilitating discussion around University policy - These focus groups will feed into annual reporting to CoG, starting Aug '24. | - This action is carried forward from our last action plan and the success measure remains the same. - Our work in this area is best reflected in our approach to consultation workshops with researchers, for instance around the next research assessment exercise, or around UKRI's recent draft EDI strategy. This approach has been strengthened by stronger relationships between the RDWG and the Readers' and Professors' representatives.
ECR5 | Encourage researchers to consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution. | - RKEO to continue support the nascent ECR network - RKEO to support Readers and Professors' representatives as necessary with events and workshops - Introduce the E/M-CR network into the University's induction processes | N | Dec-23; Aug '24 | RKEO, ECR reps | - The ECR network to hold their first event by Dec '23 - By Aug '24 we hope that the network will consist of 200 E/M-CRs | - This is a new action for 2022. - Since the last related action on this point, the ECR reps have amassed a mailing list of over 120 colleagues, conducted a survey and published a report of outcomes and established an action plan for the constituency, produced in collaboration with RKEO and PVC Research
ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community. | (Carried Forward) - We will present researchers with this opportunity to act accordingly through Research Community events and encouraging cross college/school networking. Such opportunities should be broadcast through our new RKEO newsletter. (New) - Encourage participation in consultation workshops through our growing RKEO mailing list and linked networks. - Measure attendance at these workshops and at events held by the university's four research communities, which seek to encourage engagement with trans-disciplinary issues. - Encourage an exploration of collegiality and encourage the creation of a research culture statement from the institution. | Y | Dec-23, recurring annually | RKEO | - By Dec '23, we hope that the E/M-CR and Readers/Profs networks will work together to plan at least one consultation workshop per term. - By August '25, we hope that the Communities and the networks will have contributed to a tangible improvement in research culture. This will be reflected by 80% of CEDARS respondents feeling included in their immediate research environment [Q42.4] | - This is a new action for 2022
Employment
Recruitment and induction
The aims of these obligations are to ensure recruitment of researchers is open and fair and researchers receive effective inductions into the organisation.
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices. | - Ensure that our merit-based, open and transparent recruitment processes continue to be adhered to - Continue to incorporate the work of the University EDI committee into process and policy development in this area. | N | 2025-08-01 | HR, EDI Committee | - An average of 90% researcher plus staff responding to CEDARS question 18 ('do you agree that the recruitment processes at UoW are fair, inclusive, transparent, merit-based?') in agreement. | - This is a new action for 2022 - 91% of respondents agreed with this statement in the last CEDARS and we hope to maintain this high number through continuing our good work in this area.
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position. | - Grow the reach of our Researcher Development Hub by highlighting it more regularly to SRLs and leads of Research Communities, allowing it to feed into local inductions. | N | 2023-12-01 | RKEO | - RKEO to produce a one page guide to RKEO contacts and key resources for new starters and dissemiante to all SRLs and Research Community leads | - This is a new action for 2022. - The RD Hub is a growing list of resources managed by RKEO to support self-paced researcher development and engagement with relevant parts of the university support structure (http://blog.westminster.ac.uk/researchoffice/researcher-development-hub)
Recognition, reward and promotion
The aims of these obligations are to ensure the fair and inclusive recognition of researchers as part of their career progression.
EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances. | - RKEO and RDWG to work with OD and HR in clarifying promotion pathways for researchers and making them easily accessible to staff - RKEO to plan and implement support for promotion to Reader and to Professor in the form of either a workshop or an online resource on the RD Hub | N | Dec '23 | RKEO, OD, HR | - 55% of researcher plus staff to agree that the University treats them fairly with regards to career progression in response to CEDARS Q14.4. - 55% of respondents to agree that progression policies at UoW are equitable - Updates to research-only promotion pathways confirmed and implemented by Dec '23 - RDWG to make recommendation to Research Committee concerning promotion to Reader/Professor by Dec '23 | - This action is, in part, carried over from our previous plan and the success measure remains the same - 46% of respondents felt treated fairly regarding career progression in the last CEDARS and we hope that continuing our work with the new OD team will see this figure increase
EM3 | Managers commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers. | (Carried Forward) - We will continue to monitor and evaluate managers of researchers' adherence to our inclusive, equitable and transparent recruitment and promotion policies. This will include reporting on CEDARS feedback where appropriate. | Y | Nov-2022, recurring annually | RKEO | - Include the conclusions of the RDWG's monitoring the situation in its annual (June) progress report to Court of Governors and lobby for action where appropriate. | - This action is carried forward from our last action plan and the success measure remains the same. - The RDWG continues to monitor and evaluate commitment to this.
Responsibilities and reporting
The aims of these obligations are to ensure that researchers and their managers understand and act on their obligations and responsibilities.
EM2 | Managers familiarise themselves, and work in accordance with, relevant employment legislation and codes of practice, institutional policies, and the terms and conditions of grant funding. | - HR to continue implementing effective inductions and refreshers of employment policies - RKEO to continue highlighting the number of terms, codes and procedures on its internal and external webpages to senior researchers where relevant. - RKEO to facilitate a focus group of managers of researchers to better understand gaps in understanding around CPD support/provision - Outcomes of the focus group to inform recommendations to Research Committee | N | Dec-23; Aug-25 | RKEO, HR | - 80% of managers of researchers completing CEDARS in Aug-25 to respond in question 26.3 that they feel confident guiding researchers' career aspirations and advising on relevant CPD. - RKEO to submit recommendations to Research Committee by Dec '23 | - This is a new action for 2022. - 86% of managers were confident advising on CPD in the last CEDARS, but we wish to account for the ongoing negative effects of COVID-19 by keeping the success measure here the same. - Growth in this regard will be boosted with the continuing development of our Researcher Development Hub and of our R&KE Office Communications page
ER1 | Researchers ensure that they work in accordance with, institutional policies, procedures and employment legislation, as well as the requirements of their funder. | (Carried Forward) - The mandatory online training completed by staff when they join the University covers this information but the importance of adherence to it will be compounded by stronger relationships between the RKEO and researchers. (New) - RKEO to continue to highlight policies and procedures etc available through out internal and external webpages, including the RD Hub - RKEO and RDWG, with HR, to explore the possibility of creating a researcher specific induction pack. | Y | 2023-12-01 | RKEO, RDWG, HR | - RKEO and HR to report back to RDWG on progress around prospective researcher specific induction pack by Dec '23. This should consider the different needs of research-only staff versus those on joint teaching and research contracts. | - This action is, in part, carried forward from our last action plan. The updated success measure reflects our progress to date around this issue, which is a challenge to measure.
ER2 | Researchers understand their reporting obligations and responsibilities. | - A resource on the reporting obligations and responsibilities of researchers to be created and stored on the RD Hub as well as internal facing SP Comms site. - This is supplemented by existing support around data management responsibilities and the attitude towards open research which underpins our growing research culture. | N | Dec '23 | RKEO | - The publication of a resource explaining the responsibilities of researchers around reporting by Dec '23. | - This is a new action for 2022. - The new Res Dev Hub includes new video and written resources for development around RDM and encourages staff to get in touch with the University's RDM Officer, which will be supplemented by a new resource from our Research Information Support Officer. - Next year, we will be offering school level provision to those SRLs who want the support, and an introduction to reporting (of research data RE for HEBCI, and the importance of keeping one's data up to date), as well as to data management, will be involved in this.
People management
The aims of these obligations are to ensure that researchers are well-managed and have effective and timely performance reviews.
EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent. | - RKEO and RDWG to feed into anticipated work of OD team in this area. - Effective line management for researchers results in researchers putting a lot into, and getting a lot out of, a thriving, positive, inclusive research culture. As such, this conversation around training expands into the attitudes our SRLs and senior researchers hold toward their peers and the research environment. RKEO to continue to support growth in this area with coordinated support to all schools and communities. | N | See cell H26 | RKEO, RDWG, OD Team | - At least 80% of research-only staff to respond to CEDARS Q.30.1 that their manager encourages them to engage in CPD - See cell H26 | - This is a new action for 2022. - In the last CEDARS, 81% responded positively to this question. Our renewed focus on redefining and improving research culture at Westminster is underpinned effective line management and support from and between researchers.
EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation. | (Carried Forward) - Now that the new policy is confirmed, the RDWG and RKEO should take steps to make it clear enough to managers of researchers and HR should provide appropriate training. (New) - RKEO and RDWG to explore definitions of research culture across the university through SRLs, EMCR reps and other channels, working towards an institutional statement on research culture with the support of Research Committee. | Y | Dec-23; Aug-24 | RKEO, RDWG, HR | - 80% of all respondents to CEDARS question 20 to have participated in a staff appraisal/review in the last two years. - 55% of research-only staff to agree that their line manager supports them to develop a research identity/supports them in working towards promotion opportunities in CEDARS question 28.4 in 2023. - Focus groups and workshops outlined elsewhere in this document should inform an annual narrative around research culture at UoW in its annual report to CoG and annual Concordat compliance report, starting in 2024. This research culture will hopefully feed into further conversations around a possible research culture strategy at the University. | - This action is, in part, carried over from our previous plan and the success measure remains the same - 77% of respondents in the last CEDARS had an appraisal in the last two years and we trust that the highlighting of our refined PDR process across the institution will see this figure increase. - 67% of research-only staff felt supported by their line manager wrt promotion and progression, exceeding our target. We intend to maintain this figure by expanding conversations around research culture and ensuring that the research-only staff voice is heard, through the RDWG for instance, which has a research-only staff rep from each of our three colleges.
EM1 | Managers undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care. | - Hold a consultation on researcher development with the Readers and Profs at the university through the constituency representatives to gauge where the training and development gaps are and feed this into planning for the annual RDP. | N | 2023-08-01 | RKEO, Reader/Prof Reps | - 50% responding across Q.25 of CEDARS that they feel comfortable with each competency in 2023. | - This is a new action for 2022. - This success measure is based on a small improvement from the last time we ran the survey (46%) - We have had good engagement from senior research staff at RDP workshops and seek to increase this further by increasing the number of school level sessions offered, allowing for more specifity and valuable conversations. This approach includes earlier career staff in the discussion around how they are managed and supported, fostering a more transparent research culture.
EM4 | Managers actively engage in regular constructive performance management with their researchers. | - RDWG and RKEO to continue to highlight the importance of appraisals in any relevant communication with managers of researchers and to review and monitor the situation through the meetings mentioned elsewhere in this doc with SRLs, community leads and with the representatives of Readers and Profs at the University. | N | Aug-23 See cell F26 | RKEO, RDWG | - 75% of respondents to CEDARS in 2023 who manage researchers to say that they are confident in managing the appraisal/review process effectively (question 26.4). - See cell H26 | - This is a new action for 2022 - 70% of respondents in the second CEDARS were confident in managing appraisals.
ER3 | Researchers positively engage with performance management discussions and reviews with their managers. | - Continue to highlight university promotion policies and processes at local inductions, through our SP pages and through the EMCR blackboard page. - HR continue to provide appropriate training to allow managers of researchers to carry out these reviews effectively. The new processes will be advertised to researchers through the RKEO mailing list and blog as well as through the traditional channels. | N | 2023-08-01 | RKEO, HR, ECR reps | - 60% of research-only staff responding to CEDARS in 2023 to state that they found their most recent performance review useful (question 20.a) | - This is a new action for 2022. - 63% of respondents agreed that their last appraisal was useful. A figure we aim to maintain through continued highlighting of good practice. - The RDWG continues to push for more clarity on progression pathways for research staff and is involved in ongoing discussions with HR and OD around how best to implement changes once they have been agreed.
Job security
The aim of this obligation is to improve the job security of researchers.
EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress. | (Carried Forward) - Include an institution specific question in the next CEDARS asking how well the University supports research-only staff concerns around job security. - We will continue to monitor and evaluate our researchers' thoughts on job security through surveys, RDP feedback forms and more regular meetings (New) - Make job security for researchers a focus for the EMCR network's next year of planning | Y | 2023-08-01 | RDWG, ECR reps | -Monitor the issue and include the responses in our annual report to Reserch Committee and re-evaluate the situation. | - This action is, in part, carried over from our previous plan and the success measure remains the same. - Our long term work around improving this centres around involving research-only staff in more conversations around researcher precarity. Mentoring initiatives continue and are helpful experience sharing platforms for research-only colleagues, but inviting more consultation with colleagues around this issue is key to our plans going forward.
Professional and Career Development
Championing professional development
The aims of these obligations are to promote the importance of professional development and ensure researchers have the time to engage in it.
PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors. | - RDWG to again highlight this Concordat obligation in its annual report to Court of Governors - Diversify colleagues' definitions of professional development through the continued highlighting of static, self-paced resources on our RD Hub, and explore growing those resources into self-paced programmes for researchers. - RDWG to produce a resource explaining the University's commitment to researcher development, with a high level outline of its offering of provision, to be circulated to all SRLs, KE leads and community leads for consideration. | N | Dec-23; Aug-24; Aug-25 | RKEO, RDWG | - Production of a resource outlining the University's commitment to researcher development, to be disseminated to research leaders. - The document in question should be reviewed annually, in Aug '24 and Aug '25, considering feedback and engagement data. | - This is a new action for 2022. - The RDWG continues to monitor and report on engagement with the RDP to inform the planning of future provision.
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities. | (Carried Forward) - The RDWG will report to Research Committee (and our 'Concordat Champion' - PVC Research - will then report to UEB) with an annual review of the group's progress. - The researcher specific online space mentioned elsewhere in this document will serve not only as a storage space for policy and useful training information, but an online forum for communication and feeding back on the support researchers feel they need. - Monitor attendance at all RDP events | Y | Aug-23; Aug-25 | RKEO, RDWG,PVC Research | - Submission of an annual report to PVC research and Research Committee. - An increase, year on year, in total attendance of RDP events. - In 2020/1 and 2021/2, we had 197 and 202 unique colleagues attend workshops respectively. By Aug'23 we hope this number would have reached 225 and, by Aug'25, 250. (New) - An increase in engagement with the resources available through our RD Hub. - In CEDARS '23 and CEDARS '25, we will add a question asking whether colleagues have engaged with these resources. We hope that the CEDARS'25 response rate will represent a 15% increase. | - This is carried over from our previous action plan, so the success measure remains the same. - We have submitted an annual report to Research Committee including an outline of attendances at workshops for the last two years. - We continue to monitor attendance, feedback and engagement at all workshops. Looking forward, this monitoring must be extended to our online environments, namely the youtube, RD Hub and prospective platforms for hybrid training.
PCDM3 | Managers allocate a minimum of 10 days pro rata per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development. | (Carried Forward) - Monitor and evaluate how to properly measure this target of 10 days (CPD) through consultation with researchers attending RDP events and through feedback from managers of researchers holding the new appraisals conversations. (New) - Continue to promote our new RD Hub across the institution - Continue to annually refresh the RDP and advertise it across the institution. | Y | Aug-23; Aug-24 | RKEO, RDWG | - 50% of researcher plus respondents to CEDARS Q.34 to have engaged in at least 5 days of CPD in the past year (5 days as self-defined by the researcher) - By Aug '24, we hope to have RKEO representation at every school level research committee, where updates to the RD Hub might be highlighted where appropriate. | - This action is carried forward from our previous plan and the success measure remains the same. - 29% of respondents had engaged in at least 5 days CPD in the last year in the last CEDARS. We recognise that engaging in more CPD is the end result of a medium-long term attitude shift and culture change, so we will continue our existing work around this.
PCDR1 | Researchers take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year. | (Carried Forward) - The RKEO will encourage attendance at RDP events through promoting guest academic speakers, filtering of information through school research leads, through our mailing list and blog and through the University-wide weekly newsletter. (New) - Continued higlighting of development opportunities across emerging networks and channels outlined elsewhere in this document. | Y | 2023-08-01 | RKEO | - 30% of research-only respondents to CEDARS to have undertaken at least 10 days of CPD in the past year in CEDARS 2023. | - This action is carried over from our last action plan and the target has been reduced from 50% to 30% after only 19% had undertaken 10 days CPD last year. - As outlined elsewhere, our RDP and RD Hub are both still new initiatives at UoW. Our focus is on maintaining their quality, growing their internal reach and embedding researcher development into school level and institutional planning and support. This constitutes the positive shift in our understanding of research culture outlined elsewhere in this document.
Career development reviews
The aims of these obligations are to ensure researchers and their managers are engaging in productive career development reviews.
PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers. | (Carried Forward) - Monitor the success of new career development review discussion policies from UEB and HR through CEDARS. | Y | Aug-23, and annually | RDWG | - Include evaluation of the new career development review process in the RDWG's annual report to CoG and annual Concordat compliance report from Aug '23 | - This action is, in part, carried forward from our previous action plan.
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with researcher career development reviews. | (Carried Forward) - The RDWG will report to Research Committee (and our 'Concordat Champion' - PVC Research - will then report to UEB) with an annual review of the group's progress. - The researcher specific online space mentioned elsewhere in this document will serve not only as a storage space for policy and useful training information, but an online forum for communication and feeding back on the support researchers feel they need. - Monitor attendance at all RDP events | Y | See cell F80 | See cell G80 | - See cell H80 | - This is carried over from our previous action plan, so the success measure remains the same. - We have submitted an annual report to Research Committee including an outline of attendances at workshops for the last two years. - We continue to monitor attendance, feedback and engagement at all workshops. Looking forward, this monitoring must be extended to our online environments, namely the youtube, RD Hub and prospective platforms for hybrid training.
PCDM1 | Managers engage in regular career development discussions with their researchers, including holding a career development review at least annually. | (Carried Forward) - HR will offer appropriate training in giving career development discussions in line with the new appraisals policy. - The Research Team Leadership being facilitated by Advance HE at the University for two days as part of the RDP will also improve managers' confidence in holding these conversations. (New) - To meet out target of this figure reaching 70% by the third CEDARS, we are seeking to improve our support for research specific mentoring and to incorporate the researcher perspective more clearly in higher level HR career development guidance. The creation of our Researcher Development Hub is, in part, in service of this aim, as it provides more resoruces for managers to point colleagues towards, and more information and opportunities for researchers to bring up with their managers. | Y | 2023-08-01 | HR, RKEO | - 70% of researcher plus respondents to CEDARS to describe career development reviews with their manager as useful (question 30) in CEDARS '23. - By 2025, we hope this figure will increase to 80% | - This action has been carried forward from our previous plan and the success measure remains the same. - 56% of colleagues desribed their most recent career development review as useful. A figure that we hope the embedding of new PDR processes will increase. - Again, the University's process for research staff appraisals is currently being reconstituted and it will take time for the results of these changes to become clear.
PCDR4 | Researchers positively engage in career development reviews with their managers. | (Carried Forward) - Monitor and evaluate the engagement of research-only staff with career development reviews. | Y | 2023-08-01 | RDWG, RKEO | - At least 90% of researcher plus staff to have had an appraisal in the last two years in 2023 CEDARS. | - This is action is carried forward from our last plan. - 77% in the second CEDARS had had an appraisal in the last two years. We expect this figure to rise to closer to 100% by the next CEDARS after the implementation of our improved PDR process and more work towards strengthening research culture in each school (we have recently appoint College Research & Knowledge Exchange Directors, who replaced Research Directors in each College, and are also working to appoint a KE lead in each school, working towards a joined up approach to our support for R&KE).
Career development support and planning
The aims of these obligations are to promote researchers' career development planning through tailored support and gathering evidence of professional experience.
PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers. | - With a focus on ECR development, the RDP will provide an introduction to the research funding, publishing and knowledge exchange landscapes in order to familiarise research staff with the career opportnuities available to them. | N | 2023-08-01 | RKEO | - 50% of all respondents to CEDARS agreeing that the University supports them in their broader career aspirations in Aug '23. If this figure is met, we hope the figure to grow further to 60% in 2025. If it is not met in 2023, the RDWG should explore the issue further through focus groups facilitated through the E/M-CR and Reader/Prof networks. | - This is carried over from our previous action plan. - 42% of respondents felt supported in their broader career aspirations by the university in the last CEDARS.
PCDR3 | Researchers maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications. | (Carried Forward) - Continued monitoring of the PDR process for researchers (New) - Support to be included on the RD Hub outlining the importance of keeping a CPD plan, with guidance on how to do so. - Extend the RDP to include more school level sessions, with the offer of a session focussing on careeer progression and planning. | Y | 2024-08-01 | RKEO | - 55% of all CEDARS respondents to state that they have a clear career development plan (question 29.5) in 2023. | - This is carried forward, in part, from our previous action plan and the success measure remains the same. - 39% of respondents in the last CEDARS stated that they maintain a career development plan.
Research identity and leadership
The aims of these obligations are to provide researchers with opportunity to progress in their careers by developing their research identity and leadership capabilities.
PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills. | - The launch of our Researcher Development Award in the last year has been in service of this obligation. - RKEO to continue to manage the award (awarded to a new cohort for two years each year) and review its impact. Awardees are given a small pot of money to support their researcher development, paired with a mentor and guided to find appropriate development opportunities, including leadership skills. | N | 2023-08-01 | RKEO | - The Researcher Development Award initiative should be reviewed at the end of academic year 2023/4 and the RDWG write a report for Research Committee containing outcomes and recommendations | - This is a new action for 2022.
PCDM4 | Managers identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours. | (Carried Forward) - Improve the channels of communication between researcher, manager of researcher and RKEO (New) - Continue to highlight the work of the RKEO across the institution - RKEO to continue strengthening relationships with SRLs to support them in school level strategy around research identity | Y | Aug-23; Aug-24 | RKEO | - 70% of research-only staff responding to CEDARS to say that they feel their manager supports them to develop their research identity in CEDARS 2023 - As mentioned elsewhere in this document, this area will be further supported by greater representation from RKEO at school level research committees; we aim to have reps at every meeting by Aug '2024 | - This action is carried forward from our previous plan. - 43% of respondents felt that their manager supports them in developing a research identity in the last CEDARS, which is significantly below our target. Our target may have been slightly overambitious, but we hope that the already mentioned improvements to our PDR process for researchers will support growth in this area
PCDM5 | Managers engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development. | - Readers and Profs reps to explore needs of the constituency in this area and work with RDWG and RKEO to provide solutions, with a view to a development resource or event. | N | 2023-08-01 | RDWG, RKEO | - RDWG to review findings of Readers and Profs reps and support their presentation at Research Committee. - Any recommendations should be approved by Aug '23. | - This is a new action for 2022.
Diverse careers
The aims of these obligations are to recognise, value and prepare researchers for the wide range of career options available to them within and beyond research.
PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this. | - Make working across employment sectors a focus of the EMCR network and RDWG to encourage their organising a workshop around this topic. - The E/M-CR should run a workshop exploring the barriers to working across employment sectors, supported by the RDWG and RKEO, to result in a paper detailing key barriers and suggesting ways to overcome them. | N | Aug-23; Aug-24; Aug-25 | RKEO, RDWG, ECR reps | - The paper in question should be presented to Research Committee by Aug '23 - Actions should be confirmed by Aug '23 and progress reviewed in Aug '24 - This review should inform annual evaluation of institutional support for working across sectors (next in Aug '25) | - This is a new action for 2022.
PCDM2 | Managers support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments. | (Carried Forward) - Monitor and evaluate researcher experiences in preparing for a diversity of careers through CEDARS, feedback forms from relevant RDP events and through a feedback form on a researcher specific online space. - Continue and expand our researcher mentoring circles initiative outlined elsewhere in this action plan and in our accompanying four year report. (New) - The new Researcher Development Awards scheme seeks to give time and space to researchers to consider their broader aspirations, and support through mentoring and termly workshop meetings to explore opportunities. - Further to this, the E-MCR blackboard page provides a new space for researchers to share experiences and responses to barriers faced around this. | Y | Aug-23; Aug-24; Aug-25 | RKEO, ECR reps | - 60% of researcher plus respondents to CEDARS to agree in question 22.5 that the University supports them in their broader career aspirations in 2023 - After the establishment of termly meetings of the E/M-CR network byDec '23, we hope that by 2024 they will have held meetings dedicated to careers outside of academia, including a focus group, which will inform RKEO Researcher Development Programme provision by Aug '25. | - This is carried over, in part, from our previous action plan and the success measure remains the same. - Due to the small number of contract researchers at the institution, this goal presents a significant challenge for the unviersity and it is an area we seek to continually review the barriers to.
PCDR2 | Researchers explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments. | - RKEO and RDWG to work with schools on emerging mentoring schemes and incorporate working across sectors into these schemes - RKEO to explore possibility of external coaching for ECRs, with an explicit focus on this. - Mentoring included in RDAs to include this topic area. | N | 2023-08-01 | RKEO, RDWG | - Inclusion of this area in at least the pre-existing College mentoring circles initiative and RKEO to meet with each school to explore further initiatives. - Progress trackers which form part of RDAs to include consideration of working across sectors. - RDWG to survey mentoring needs through the E/M-CR network and submit a report of recommendations to Research Committee by August '23 | - This is a new action for 2022.
PCDR6 | Researchers consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation. | - Grow the integration of KE and collaboration in the RDP and RD Hub - Effectively promote the opportunities for support in this area available from our new Collaboration Team - Maintenance of our policy engagement webpage for staff (this is updated weekly with new policy engagement and government consultation opportunities) | N | Dec-23; Aug-25 | RKEO, Collaboration Team | - Annual workshops from the Collaboration Team aimed at engaging conversation around KE, consultancy and commercialisation - Publication of a blog series on Innovation and Collaboration by Dec '23 - By Aug'25, the RDWG should conduct a five-year review of the RDP, with a set of recommendations concerning growing the integration of KE and collaboration into research support at UoW | - This is a new action for 2022
* The Researcher Development Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Researcher Development Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.

## Abbreviations and links
| Further hyperlinks and supplementary information |  |  | Abbreviations and glossary
1 | Researcher Development Hub | https://blog.westminster.ac.uk/researchoffice/researcher-development-hub/ | CEDARS | Culture, Employment and Development in Academic Research Survey
2 | R&KE Office Blog | https://blog.westminster.ac.uk/researchoffice/ | CPD | Career and Professional Development
3 | R&KE Ethics and Integrity Webpages | https://www.westminster.ac.uk/research/research-and-knowledge-exchange-governance | CRD | College Research Director
4 | R&KE Office Youtube Channel | https://www.youtube.com/channel/UCKQ2lMy0iHe9FIpVHid5Wwg | CREC | College Research Ethics Committee
5 |  |  | CROS | Careers in Research Online Survey
6 |  |  | DI | Diversity and Inclusion
7 |  |  | DRDP | Doctoral Researcher Development Programme
8 |  |  | E&C | Environment and Culture
9 |  |  | E/M-CR | Early/mid-career researcher(s)
10 |  |  | EDI | Equality, Diversity and Inclusion
11 |  |  | FRD | Faculty Research Director (We now have CRDs)
12 |  |  | FREC | Faculty Research Ethics Committee (We now have CRECs)
13 |  |  | HOD | Head of Department
14 |  |  | HOS | Head of School
15 |  |  | HR | Human Resources
16 |  |  | HRERA | Human Resources Excellence in Research Award
17 |  |  | HRM | Human Resource Management
18 |  |  | HROD | Human Resources and Organisational Development
19 |  |  | KE | Knowledge Exchange
20 |  |  | LMS | Learning Management System
|  |  | LOD | Learning and Organisational Development
|  |  | MI | Management Information
|  |  | OD | Organisational Development
|  |  | PI | Principal Investigator
|  |  | PIRLS | Principal Investigators and Research Leaders Survey
|  |  | PPCD | Personal and Professional Career Development
|  |  | PDR | Personal Development Review
|  |  | PDF | Personal Development Framework
|  |  | RDF | Vitae Researcher Development Framework
|  |  | RDP | Researcher Development Programme (This programme is to be available both to research-only staff and those on academic and research contracts)
|  |  | RDWG | Researcher Development Working Group
|  |  | REC | Race Equality Charter
|  |  | RKEO | Research and Knowledge Exchange Office
|  |  | R&KE | Research & Knowledge Exchange
|  |  | SES | Student Experience Survey
|  |  | SLD | Staff Learning and Development
|  |  | SP | SharePoint
|  |  | SRL | School Research Lead
|  |  | TNA | Training Needs Analysis
|  |  | ToR | Terms of Reference
|  |  | UEB | University Executive Board
|  |  | UoW | University of Westminster
|  |  | UREC | University Research Ethics Committee
|  |  | WAM | Workload Allocation Modeller