## 2020-24 Action Plan
HREiR Action Plan 2020-22 (2022 Update)
Details
| Institution name: | University of Westminster | The institutional audience* for this action plan includes:
| Cohort number: | 13 | Audience | # | Comments
| Date of submission: |  | Research staff | 68 | Combined with research and teaching staff to form a 'Researcher Plus' category
Postgraduate researchers
|  |  | Research and teaching staff | 842 | Combined with research only to form a 'Researcher Plus' category
Teaching-only staff
Technicians
Clinicians
Professional support staff
Action Plan |  |  | Other (please provide numbers and details):
Column | Obligation | Action | Success Meaure (SMART) | Deadline | Responsibility | Progress upadate | Outcome/result | Old Concordat principle and clause
| Obligation | Action | Success measure (SMART) | Deadline | Responsibility | Progress update (to be completed for submission) | 2022 Update | Old Concordat principle and clause
Environment and Culture
Institutions must:
ECI1 | Ensure that all relevant staff are aware of the Concordat | - Provide physical (at our, 'Welcome to Westminster' events) and digital (as part of a researcher specific induction pack) copies of the Concordat during the researcher induction process. - At relevant RDP sessions, draw attention to how the session fulfills the obligations of both the institution and the researcher as set out in the Concordat. | - At least 50% of research-only staff to respond to the relevant CEDARS question (42.1) as having an understanding of the Concordat to Support the Career Development of Researchers. | Upon completion of the second CEDARS (UoW is running CEDARS for the first time this year - 2020/1). | RKEO, HR | This is a new action for 2020. | - Plans for in-person inductions from the RKEO were made unrealistic by the implications of COVID-19. To support a culture of continual development, our Researcher Development Hub was created. - This hub comprises a growing bank of self-paced development resources, listings of upcoming live workshops, and acts as a space for storage of important documents, like the Concordat. It forms an important part of RKEO induction conversations with new starters (held informally between RKEO and new starters), whilst also being a useful resource for annual appraisal conversations and general self-reflection. - Attention has been drawn to the Concordat at relevant workshops, such as our recent consultation on the new UKRI EDI strategy, and at meetings of the new RKEO Grant Writing Group. - Our success measure was marginally missed (46% of res-only staff, but 52.1% of researcher-plus staff) and the new hub will hopefully improve this further. - This will be carried forward to our new action plan (2022-2025) | New
ECI2 | Ensure that institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers | - To ensure that the inclusivity, equitability and transparency of policies relevant to researchers continues, the RDWG should retain its line of communication with the unviersity EDI Committee, so that the two can feed into eachother's strategising as appropriate. - Review the research staff internal and external facing webpages to ensure that our policies are clearly published. - Increase our engagement through, and encourage researcher interaction with, the RKEO blog and twitter account to broaden channels of communication. - Start a monthly RKEO newsletter giving updates on research at UoW, funding opportunities, training opportunities etc, as well as policy updates. | - A mean average of 65% of researcher plus staff responding to CEDARS qu. 13 (agreement that the institution treats you fairly in relation to…) to agree they are treated fairly. - An increased online presence. Our RKEO twitter account aims to have 1000 followers. | Upon completion of the third CEDARS. | RKEO, RDWG, EDI | This action is, in part, carried over from a previous point set out in row 38 of our 2016 Action Plan (as below): Design a dedicated research staff website for researcher development and researcher career opportunities on the University intranet to include all relevant information needed such as links to external organisations e.g. Euraxess, Vitae, and to Vitae’s RDF and the Concordat and link to the VRE as appropriate. As much as we do have a dedicated internal site for the communication of information relevant to researchers, we want to improve it by making development resources available there as well as increasing its reach through developing our channels of communication with colleagues. The long term deadline on this action is to account for the number of sub-points and to account for the time it takes for new practice and policy to be properly disseminated throughout the institution. | - The RDWG has expanded its membership to include a representative from the University's Q+ (LGBTQI+) network, the BME network, our Disability network, and the Women of Westminster network - A review of our external web pages is ongoing and the RKEO are feeding in directly. We have also redesigned our internal RKEO SharePoint Communications site to make important policies pertaining to EDI more accessible. - The RKEO mailling list now has over 1100 subscribers, who receive a monthly newsletter. Engagement with this newsletter (number of people following links) has grown by 4% in the last year. We also now have a separate mailling list of 120+ early-career researchers, who received targeted comms from the institutional ECR reps. - The quantitative aims here were longer term and look to be achieved by 2024. The UoW RKEO twitter account currently has 815 followers and the mean average response to Q.13 this year was 55%. Improved appraisal processes and growing relationships between prof services and academic staff will hopefully see this improve by 2024. - This will be carried forward to our new action plan | P2.1 P6.8
ECI3 | Promote good mental health and wellbeing through, for example, the effective management of workloads and people, and effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues | - Through our increasing online presence and at relevant RDP sessions, encourage research staff to engage with the 'Juice' platform, which promotes good health and wellbeing through a series of events, talks and sessions. - Continue to promote the work of our Health Innovation and Wellbeing Research Community through the publication of annual reports and through our RKEO newsletter. - As well as drawing attention to it at induction, draw focus to our 'Diversity and Dignity at Work and Study Policy' in an online space for research-only staff in particular. | - At least 65% of researcher plus respondents to CEDARS q.41.4 to agree that UoW actively promotes the importance of good mental health and wellbeing. - 50% of research-only staff to respond in CEDARS that they are familiar with UoW processes for reporting bullying or harassment and 60% to trust that the institution would handle any such claim fairly. | Upon completion of the third CEDARS. | RKEO | This is a new action for 2020. The longer term deadline on this action is to account for the University's commitment to the 'Juice' platform being relatively new, as is the production of a research newsletter and establishment of a researcher specific online space. | - Staff continue to engage with the 'Juice' program. This is bolstered by emerging workshops and programmes from the new Organisational Development team. - The HiW Research Community has a regular spot in our newsletter and their work is promoted through this, through the RKEO twitter, and at researcher development events where appropriate (for instance through our recent internally led grant writing programme). The Communtiy hold regular events bringing together researchers across HiW. - The 'Diversity and Dignity at Work and Study Policy' can be found at the Researcher Development Hub. - 66% agreed with Q.41.4; 63% are familiar with the processes for reporting bullying or harassment and 88% belive the institution would investigate fairly. - This action is complete. | P6.9
ECI4 | Ensure that managers of researchers are effectively trained in relation to equality, diversity and including, wellbeing and mental health | - As well as offering the Advance HE two day training in research team leadership and ensuring that all new staff undertake compulsory online D&I training, the institution should make the University research strategy available on a researcher specific online space to be referred to where necessary. - Our Diversity and Inclusion Research Community and Health Innovation and Wellbeing Research Community offer workshops and talks throughout the year - at least once per term - highlighting the University's commitment to these issues. Going forward, there should be more of a focus on exploring the impact of this commitment with managers of researchers and more of an effort to engage them with the Research Communities' work. - Lobby the University to review the provision of diversity training and repeat training at that. | - 75% of researcher plus respondents in CEDARS agreeing that the institution is committed to equality and diversity. | Upon completion of the second CEDARS. | RKEO, HIW Community, DI Community | This is a new action for 2020. | - Compulsory D&I training is still in place and the Research & Development strategy is available on our external facing web pages. Further to the compulsory generic training, our new OD team's development programme for 2022 includes 'Understanding Microaggressions and its Impact', 'Aurora Women Leadership Development' and 'Union Black: Britain's Black Cultures and Steps to Anti-Racism' - A recent change in the leadership of our Diversity and Inclusion Research Communtiy has meant that the way they organise events has changed slightly, but the community remains an important mechanism for advocating research motivated by EDI concerns. - Our target from the CEDARS was exceeded by seven percent. - We have not offered Advance HE's RTL workshop in-house this year, but are looking to do so next year for SRLs and our Research Community leadership. - 82% of respondents agreed that the institution is committed to equality and diversity - This action is complete | P2.3
ECI5 | Ensure that researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity | - Include the Concordat to Support Research Integrity in an online space of important documents for research staff and include it in a digital researcher induction pack. This document should be understood in the context of our Code of Research Good Practice. - Condense our pre-existing ethics training session to under two hours and run it three times a year, disseminate (both online and in print) an easy to digest poster of the ethical approval process at UoW and encourage engagement in both resources through our growing online presence and through effective promotion of our new RDP. | - Offer three ethics sessions per year and achieve an attendance of 50 across them. - At least 30% of researcher plus CEDARS respondents to state that they have an understanding of the Concordat to Support Research Integrity. | Upon completion of the second CEDARS. | RKEO, CRECs, UREC | This is, in part, carried over from a point outlined in row 38 of our previous action plan (as below): An open programme of ten 90 minute research ethics training for research staff commissioned from Association for Research Ethics or equivalent provider. RKEO have decided that 10 is not an appropriate amount of sessions to run as it may lead to waning attendances. We will include three per year in our RDP. | - The Research Integrity Concordat is being included in an ongoing redesign of our external webpages and is available on the Researcher Development Hub. - Our ethics training session is now two hours long and runs termly, with regular attendance. - Rather than publishing a poster, we have stored several videos concerning ethics on our Researcher Development Hub and continue to add to this bank as appropriate. - Our target number of workshop attendees was exceeded by nine, but our CEDARS target around the Concordat was missed, with 16% having an understanding of the Research Integrity Concordat. We seek to improve advocacy of good research integrity and related initiatives/policy through our redeveloped webpages, which are currently in development. - This action will be carried forward to our new action plan | P6.1
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and use the outcomes to improve institutional practices | - The RDWG (comprising research-only staff, ECR academic and research staff, senior academics and professional services representation) will meet once per semester to monitor the quality of the research environment and culture. - Further to this, each RDP session feedback form present an opportunity for researchers to anonymously give their thoughts on UoW E&C, which will be discussed at RDWG where appropriate and taken further where necessary. | - 70% of all researcher plus respondents to CEDARS claiming to feel valued at work. | Upon completion of the third CEDARS. | RKEO | This is a new action for 2020. The longer term deadline here, as outlined in our four year report, is to account for the significant changes to the way we support researchers at Westminster and the time it takes for changes like this to pay dividends. | - The RDWG has continued to meet regularly to discuss developments in researcher development across the institution and evaluate junctures at which it can positively contribute towards research culture growth (for instance in PDFs and in work with OD team) - RDP session attendees have been reluctant to give open feedback on E&C. The new ECR network hopes to gauge colleagues' thoughs on research culture more effectively and feed this into the RDWG. - We hope to achieve this response target by the time we run CEDARS for the third time. 62% of respondents felt valued at work at the last time of asking. - Our regular engagement with CEDARS itself is in service of realising this action. - This action will be carried forward to our new action plan. | P6.10 P7.5
Funders must:
ECF1 | Including requirements which promote equitable, inclusive and positive research cultures and environments in relevant funding calls, terms and conditions, grant reporting, and policies | x | x | x | x | x | x | P6.6
ECF2 | Consider how funding opportunities and policies can facilitate different patterns and ways of working, and promote the wellbeing and mental health of researchers | x | x | x | x | x | x | New
ECF3 | Ensure that funding call requirements and selection processes offer equality of opportunity between different groups of researchers, recognise personal contexts, and promote positive research cultures and working conditions | x | x | x | x | x | x | P6.6
Managers of researchers must:
ECM1 | Undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work | - The provision set out in cell C20 will be coupled with an increase in encouragement from the RKEO directly, from its increasing online presence and from Research Community facilitators for managers of researchers to engage with the University's four Research Communities - especially the Diversity and Inclusion Community. | - In response to our institution specific additional CEDARS question, at least 80% of researcher plus staff to say that they have an understanding of our Research Communities. - 90% of respondents to CEDARS identifying as a manager of researchers, to say that they have an understanding of our Research Communities. | Upon completion of the third CEDARS. | RKEO, CRDs | This is, in part, carried over from a point outlined in row 34 of our previous action plan (as below): Deliver an annual leadership training programme for academic leaders and managers across the University, designed and run in-house to enhance leadership and line management skills for Academic leaders As well as tailoring in-house RDP sessions for managers, we will run the two day Advance HE, Research Team Leadership programme for emerging leaders. As outlined in our four year report and supplementary case study, our Research Communities are a new initiative and as such, it is appropriate to set a longer term deadline here. | - 81% of researcher-plus colleagues responding to CEDARS have an understanding of the Westminster Research Communities - The number of managers of researchers responding to this question in the last CEDARS was too small for the data to be useful. - The Diversity and Inclusion Community now has a new academic lead, who is in the process of making an action plan for the Community. Short term actions will include engaging the community to actively contribute to our institutions response to the draft EDI strategy from UKRI and using that consultation process as a springboard for internal change. - The Community are also set to be involved in a new initiative from our Collaboration Development Team, seeking to form small focus groups looking at specific research related EDI barriers to collaboration with external partners, drawing up a resource based on current best practice to implement and disseminate across the university in due course. - We continue to explore the best ways to approach training and development wrt to EDI - This action will be carried forward to our new plan | New
ECM2 | Ensure that they and their researchers act in accordance with the highest standards of research integrity and professional conduct | See cell C21. - The emphasis on managers to encourage optimum engagement with the relevant training and support should come from school research leads as well as RKEO. - The RKEO will make the importance of ethics training clear to managers of research-only staff in particular through directed email communication, through the Research Communities and our growing online presence. A focus on ethics as a key pillar of the trainnig programme for research-only staff and their managers will be stressed in the RDP Handbook. | See cell D21. - All managers of research-only staff to be sent the recording of our generic researcher ethics training session, 'Ethical Considerations'. | 2021-09-01 | RKEO, School Research Leads, Research Communities | See cell G21. | - All managers of researchers now have access to the R&KE Office self-service ethics videos - The 'Ethical Considerations' workshop is not recorded due to its becoming increasingly interactive in nature. The session is however run three times per year and all SLRs receive monthly updates on training sessions being held to encourage engagement. - Ethics (and relevant training opportunities/development in policy or guidance) is written out about in our monthly R&KE Office newsletter, often referenced in our growing blog and, when not appropriate for external audiences, highlighted as appropriate on our SharePoint Communications site for internal staff. - This action is complete | New
ECM3 | Promote a healthy working environment that supports researchers' wellbeing and mental health, including reporting and addressing incidents of discrimination, bullying and harassment, and poor research integrity | - The increased availability of the 'Diversity and Dignity at Work and Study Policy', as set out in cell C19, will allow managers of researchers to engage with the document more easily. | - 80% of managers of researchers to say that they are confident in responding to issues pertaining to health and wellbeing in CEDARS. | Upon completion of the second CEDARS. | RKEO | This is a new action for 2020. | - 86.8% are confident with this. - The policy is available on the R&KE Office SharePoint Communications site and Researcher Development Hub. - The growth of our institutional Organisational Development Team will hopefully further support expansion in this area, with an impetus on wellbeing intended to form a core part of their programme offering for next year. - This action is complete | P6.9
ECM4 | Consider fully, in accordance with statutory rights and institutional policies, flexible working requests and other appropriate arrangements to support researchers | - Planned Advance HE Research Team Leadership training will improve capabilities in this area. - HR partners work to support research managers with requests. - Planned 'Research Relationships' training. | - A more flexible working environment with healthy researcher-line manager relationships. 70% of managers of researcher staff to describe themselves as confident in managing flexible working requests. | Upon completion of the second CEDARS. | RKEO, HR | This is a new action for 2020. | - The RTL workshop was run successfully, with all feedback rating the session 4 or 5 star. The workshop has since been dropped from our programme, but managers have, naturally, grown more comfortable with colleagues working flexibly in the context of the COVID-19 pandemic. - Research Relationships training was run effectively last year and is being run again this year with a view to supporting ECR interpersonal skills. - 65.7% described themselves as confident in managing flexible working requests. This perhaps surprisingly low figure was captured less than three months after the initial switch to home working in the UK however. We marginally missed our CEDARS target here, and will remodel our success measure in a new forward-facing action plan. - This action is complete | New
ECM5 | Engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | - Elected ECR and Readers and Profs reps on Reseach Committee to be enaged in policy development and co-opted onto working groups where relevant. The amplification of their voices will lead to better university-wide knowledge of the RDWG, it's work and, by consequence, surveys like CEDARS. | - A 25% University wide response rate to CEDARS and a 35% response rate in research-only staff and their managers. | Upon completion of the third CEDARS. | RKEO, RDWG | This is a new action for 2020. Raising awareness and highlighting the use of the CEDARS in the context of growing researcher development provision at the University is a gradual process, hence the longer term deadline. | - After running the CEDARS twice, we have agreed that this aspirational response rate target is over ambitious due to the composition of our target group (all research staff and all teaching & research staff). - We will continue to seek to grow the profile of this survey internally to increase this response rate, but also look for other metrics as success measures (internal surveys, school-level data etc) - Our focus on staff networks and constituency reps, and intention to continue building a culture of consultation for our academics, feeds into progress in this area. - This action is closed | New
Researchers must:
ECR1 | Actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students | - The need to support newer colleagues in this regard should be addressed by ECR representation on both research committee and in our RDWG. - Training focussed on strengthening upwards and downwards working relationships will contribute to this end. - RKEO to encourage engagement with our staff networks by disseminating EDI group actions and events to researchers through the RKEO newsletter and online channels. | - 70% of researcher plus respondents to CEDARS to state that they feel valued at work - A welcoming, healthy, supportive research culture. | Upon completion of the third CEDARS. | RKEO, RDWG, EDI | This is a new action for 2020. Our work in this area is strong and setting this slightly longer term deadline allows for the highly positive response in CEDARS set out here. | - In the second CEDARS, 62% of staff said that they felt valued at work. - The actions outlined here have been addressed in a series of ways. ECR representation has been strong on Research Committee and in the RDWG, with the reps going as far as to establish a network for their peers to communicate, exchange ideas and feed into high level discussions to which the reps themselves are privy. - The RKEO feeds into the annual institutional EDI action plan review and are becoming increasingly involved in conversations pertaining to cross-school/college work, for instance in the strategising of our research communities. Workshops co-ordinated by the RKEO this year to encourage discussion around research culture include a session for Readers and Professors to contribute to the updating of our institutional Research & KE strategy, and a session inviting repsonses from across the university to UKRI's draft EDI strategy, allowing a range of voices to inform our response to the consultation call. - This action will be carried forward to our new action plan. | New
ECR2 | Ensure they act in accordance with employer and funder policies related to research integrity, and equality, diversity and inclusion | - We will increase researcher engagement with the UoW Code of Research Good Practice by advertising the document in a researcher specific online space and through pointing towards it at relevant RDP sessions. - Research Ethics training sessions run by UREC and the RKEO should be re-evaluated and run three times per year (one with each CREC chair). | - At least 50 researcher plus colleagues per year to attend the Research Ethics Session. | 2022-07-01 | RKEO | This is relevant to a previously closed action, outlined in row 27 of our previous action plan (as below): Raise awareness and understanding of Westminster’s University Research Governance Framework and Code of Practice for Research We will look to continue our good work in this area and expand the scope of our communications. | - 59 colleagues attended this workshop last year, exceeding our target. - The Code of Research Good Practice is easily accessible on our external web pages and on our new Researcher Development Hub. - The RKEO continues to engage in sector-wide conversations around EDI policies and policies internally and externally with our university EDI committee, DI Research Community and through consultations with funders/UKRI, as well as attendance at Vitae etc events. - This action is complete | P5.3
ECR3 | Take positive action towards maintaining their wellbeing and mental health | See cell C19. | See cell D19. | See cell E19. | RKEO | See cell G19. | x | New
ECR4 | Use available mechanisms to report staff who fail to meet the expected standards of behaviour, particularly in relation to discrimination, harassment, bullying, and research misconduct | - We must draw attention to our, 'Diversity and Dignity at Work and Study Policy' through placing it in a researcher specific online space and provide physical copies of it at the 'Welcome to Westminster' induction. - Compulsory online onboarding training covers basic procedures of how to report misconduct of any kind. | - At least 60% of researcher plus respondents in CEDARS to say they are familiar with UoW mechanisms for reporting harassment and bullying. | Upon completion of the second CEDARS. | RKEO | This is relevant to a previously closed action, outlined in row 26 of our previous action plan (see below): Raise Awareness of the revised Dignity at Work Policy and Flexible Working Policy manager’s responsibilities within the policy via a programme of Leadership and Management Development. New initiatives for disseminating information and guidance to researchers outlined in this document will help us continue our good work on this. | - 57.5% of respondents in the last CEDARS said they were familiar with mechanisms to report bullying or harassment. Falling just short of our target, this area has been progressed further since the second CEDARS by the rollout of our new "Report and Support" platform. This platform is a result of work from our new organisational development team, who the RDWG will work more closely with going forward. - This action will be carried forward to our new plan. | P6.9
ECR5 | Consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | - See cell C32. - RDWG and RKEO to review the feasiblity of reimagining and re-starting the UoW Researcher Network. Consultation with school research leads, all research-only staff and mentoring circle group leaders should take place to explore the possibility of establishing an ECR network of those to have been through the year long mentoring circle initiative, developing a cohort mentality and encouraging contribution to policy from researchers across all colleges. | - Ongoing monitoring of the potential to (re)launch the researcher network and a decision to be made within two years. | 2022-08-01 | RKEO, RDWG | This is a new action for 2020. | - The E-M/CR constituency representatives on university Research Committee have amassed a network maililng list of over 120 colleagues and are seeking to organise termly events from next year. - These events will include opportunities for contribution to institutional policy development. The discussions of the Researcher Development Working Group, on research hours or researcher development provision for instance, will invite the thoughts of network members. - The Readers and Professors at the university have also recently elected three new representatives, who each mentioned engaging a more diverse range of voices in policy development conversations in their candidate statements. The RKEO will seek to facilitate these conversations. A recent workshop organised by the previous reps, seeking insights on updates to our institutional R&KE strategy, was a good starting point. - The action is complete | P3.13
Employment
Institutions must:
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices | - Make our recruitment policies more easily available on a researcher specific online space - Include researcher insights on recruitment gained through CEDARS in the RDWG annual report to Research Committee. | - An average of 65% researcher plus staff responding to CEDARS question 18 ('do you agree that the recruitment processes at UoW are fair, inclusive, transparent, merit-based?') in agreement. | Upon completion of the second CEDARS. | RDWG, RKEO | This is a new action for 2020. | - This target was exceeded significantly, as 91.7% agreed that the recruitment process was fair. - Aligning with our recruitment policies, and its conflation with our EDI strategies and policies, is a core part of our research management training. - This action is complete | P1.2 P6.2 P6.7
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position | - Design a pack of supplementary induction materials specifically for research staff to be distributed digitally with the general onboarding information in 2020/1. This should include guidance on internal policy and clear information on the support avaliable through the RKEO, as well as copies of important documents outlined elsewhere in this action plan. | - At least 60% of researcher plus new starters in 2020/1 to have accessed the researcher specific induction pack and attended a Researcher Development Programme session. | 2021-07-01 | RKEO, RDWG | This is a new action for 2020. Our induction processes for researchers are being re-imagined at present for implementation in 2020/1. This change, again, will take several years to take hold and pay dividends, hence the longer term deadline. | - This action has been re-shaped after the establishment of our Researcher Development Hub, a website dedicated to researcher development for new and more experienced researchers to establish/refresh their understanding of universal areas of development and also of UoW specific structures, processes and policies. - These materials are highlighted to all new research staff by the RKEO directly. (http://blog.westminster.ac.uk/researchoffice/researcher-development-hub/) - The RKEO reaches out to new academic staff to bring this resource to their attention. - This action is complete | P3.6
EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances | - Advertise our progression pathways and guidance more effectively on a researcher specific online space. This information should also be included in the supplementary researcher induction pack. | - 55% of researcher plus staff to agree that the University treats them fairly with regards to career progression in response to CEDARS Q14.4. | Upon completion of second CEDARS | RKEO | This is, in part carried over from a point outlined in row 42 of our previous action plan (as below): Implement a new career progression framework Our progression pathways are not clearly signposted to enough at present and we will seek to remedy this. | - 46% of respondents agreed with this question. - The more relevant CEDARS question is in fact asking whether respondents feel that progression policies are equitable - the positive response to this Q is 37.4% - The progression guidance for research routes is being updated at present and the RDWG will feed into discussions around it going forward. - Once this process and guidance has been confirmed, the RKEO plan to run workshops for colleagues in promotion to reader and to professor, to train managers in explaining the longer term planning, and to embed these processes into prospective new mentoring initiatives. - This action will be carried forward to our new plan | P2.6 P6.3 P6.4 P6.7
EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent | - Run Advance HE's Research Team Leadership programme over two days at the University for emerging leaders. - Encourage managers of research-only staff not only to take part in RDP events centred around 'taking charge of your career' aimed at ECRs and MCRs as guest speakers, but as participants. This encouragement will come through improved relationships with the RKEO and its increased online presence. | - At least 70% of research-only staff to respond to CEDARS Q.30.1 that their manager encourages them to engage in CPD | Upon completion of the second CEDARS | RKEO | This is a new action for 2020. | - 81% agree that they are encouraged to engage in CPD by their line manager. - The Advance HE training mentioned will not be run again going forward, but the RKEO will feed into future research management training, will encourage the OD team to incorporate research motivations better into their institutional management training, and work with the Research Communities where appropriate, to support their provision for emerging leaders and research managers. The long term aim of our new Researcher Development Awards initiative works towards this same end. - This action is complete | P2.3
EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation | - University policy on appraisals/reviews has been under review at UEB and the RDWG has fed into the discussion along with HR. The result is a re-imagined PDR process with a clear focus for all research staff. Attention to this highlights the University's intention to support research staff in personal development and demonstrates how much the university values researchers. These efforts are motivated by our intention to retain excellent research staff and to fuel career progression leading to excellent research. - Now that the new policy is confirmed, the RDWG and RKEO should take steps to make it clear enough to managers of researchers and HR should provide appropriate training. | - 80% of all respondents to CEDARS question 20 to have participated in a staff appraisal/review in the last two years. - 55% of research-only staff to agree that their line manager supports them to develop a research identity/supports them in working towards promotion opportunities in CEDARS question 28.4 | Upon completion of the third CEDARS. | RKEO, RDWG, HR, UEB | This is, in part, carried over from a point outlines in row 32 of our previous action plan (as below): Review use of PPDRs (Appraisals) for researchers, ensuring that managers of researchers are able to hold effective PPDRs and one-to-ones that are motivating for researchers, identifies the career and personal development needed by them and leaves them feeling valued members of the University The University no longer uses the PPDR process system but is working towards a new solution. Our appraisals processes for researchers are being re-imagined at present and these positive changes will take several years to pay dividends, hence the longer term deadilne here. | - The effects of the outlined changes to our appraisals process will take some time to make themselves evident, but 77% of respondents having had an appraisal in the last two years is a promising figure at this point. - 67% of research-only staff feel supported by their line manager wrt promotion and progression, which exceeds our target. - Looking forward, the RKEO will push for the embedding appraisal processes, and support with career progression through our RD Hub, in RKEO induction conversations and with the way our research-only staff are managed. - This action will be carried forward to our new plan | P2.6 P6.3 P6.4
EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress | - To encourage discussion of this issue between researchers, we will continue our college researcher mentoring circles initiative. The initiative should be better publicised online to attract more research-only colleagues to take part. - We will continue to monitor and evaluate our researchers' thoughts on job security. | - Include an institution specific question in the next CEDARS asking how well the University supports research-only staff concerns around job security. Include the responses in our annual report to Reserch Committee and re-evaluate the situation. | Upon completion of the second CEDARS | RDWG, RKEO | This is a new action for 2020. | - We did not include this question in the latest CEDARS after consultation with internal stakeholders. - Our long term work here includes involving research-only staff in more conversations around researcher precarity. Mentoring initiatives continue and are helpful experience sharing platforms for research-only colleagues, but inviting more consultation with colleagues around this issue is key to our plans going forward. - This action will be carried forward into our new plan | P1.3 P2.1 P2.2
EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making | See cell C32. - Monitor the effectiveness of the number of research staff on both research committee and the RDWG. Evaluate the impact of this level of representation and increase if necessary. If there is the demand to contribute to these groups, we could perhaps consider rotating representation annually. | See cell D32. - Monitor and evaluate the participation of research only staff on decision making bodies annualy with a view to maintaining an appropriate level of representation each year. - We should take into account CEDARS responses where appropriate, for instance question 15.7 (does the University value your contribution to policy?) | 2024-07-01 | RKEO, RDWG | See cell G32. | - Our success measure for this action was not as robust as it could have been. Monitoring this engagement has been a challenge but is ongoing. - Through holding more consultation workshops around prominent changes to external and internal policies and initiatives, we hope to best embody this concordat priniple and measure engagement through attendance figures. - This action will be carried forward into our new plan | P3.13
Funders must:
EF1 | Include requirements which support the improvement of working conditions for researchers, in relevant funding calls, terms and conditions, grant reporting, and policies | x | x | x | x | x | x | P2.4
EF2 | Review the impact of relevant funding call requirements on researchers' employment, particularly in relation to career progression and lack of job security | x | x | x | x | x | x | New
EF3 | Support institutions to develop policies and frameworks to promote sustainable employment arrangements and enhance job security, and provide opportunities for career progression | x | x | x | x | x | x | P2.4
EF4 | Consider the balance of their relevant funding streams in providing access to research funding and its impact at all career levels | x | x | x | x | x | x | New
Managers of researchers must:
EM1 | Undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care | - We will advertise a sub-group of activities together in the RDP to be aimed at senior academics and managers of researchers. RKEO will encourage engagement with these sessions through its growing online presence and through utilising not only our new newsletter, but school specific mailings lists. | - 30% of managers of research-only staff to have attended an RDP organised session in the academic year. | 2022-07-01 | RKEO, RDWG. | This is a new action for 2020. | - This success condition has proven difficult to measure due to our turnover of research-only staff. - We have had good engagement from senior research staff at RDP workshops and seek to increase this further by increasing the number of school level sessions offered, allowing for more specifity and valuable conversations. This approach includes earlier career staff in the discussion around how they are managed and supported, fostering a more transparent research culture. - This action is closed | P2.3
EM2 | Familiarise themselves, and work in accordance with, relevant employment legislation and codes of practice, institutional policies, and the terms and conditions of grant funding | - As outlined elsewhere in this document, ensure that relevant legislation, codes of practice and institutional policies are published in easily accessible areas, namely a researcher specific online space. This understanding will allow managers of researchers to more effectively guide those who they line manage to the most impactful training sessions and sources of information. | - 80% of managers of researchers completing CEDARS to respond in question 26.3 that they feel confident guiding researchers' career aspirations and advising on relevant CPD (including meeting the conditions of external funding grants, working in accordance with codes of practice etc). | Upon completion of the third CEDARS. | RKEO | This is a new action for 2020. The establishment and publicising of this researcher online space (in the pre-existing RKEO blog) will take time to cement itself, hence the longer term deadline. | - 86.8% of managers of researchers are confident guiding researchers' career aspirations and advising on CPD. - Further growth in this regard will be boosted with the continuing development of our Researcher Development Hub and of our R&KE Office Communications page - This action is complete | P2.2
EM3 | Commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers | - We will continue to monitor and evaluate managers of researchers' adherence to our inclusive, equitable and transparent recruitment and promotion policies. This will include reporting on CEDARS feedback where appropriate. | - Include the conclusions of the RDWG's monitoring the situation in its annual progress report to Research Committee and lobby for action where appropriate. | Annually, each July, starting in July 2021. | RDWG | This is a new action for 2020. This action is to monitor the situation; a monitoring which should be ongoing on an annual basis moving forward. | - This action is ongoing. We continue to reflect institutional adherence to equitable recruitment and promotion policies in our annual report to Research Committee (each November). - The RDWG continues to monitor and evaluate commitment to this. - This action will be carried forward to our new plan | P6.3
EM4 | Actively engage in regular constructive performance management with their researchers | - Once the institutional policy is confirmed, HR should provide appropriate training for managers of researchers in holding standardised permformance management review conversations. | - 70% of respondents to CEDARS who manage researchers to say that they are confident in managing the appraisal/review process effectively (question 26.4). | Upon completion of the third CEDARS. | RKEO, HR, UEB | This is carried over, in part, from a previous action outline in row 33 of our 2016 Action Plan (see below): HRERA Steering Group will report to the University HR Committee who in turn report to the Court of Governors. Formally review the progress of the Action Plan each academic term and at the end of Year 1 and Year 2 The already mentioned re-designing of our appraisal/review processes for researchers may take time to take hold and prove universally successful, hence the longer term deadline. | - 70% of respondents to the second CEDARS were confident at managing appraisals. - This action is complete | P2.3
EM5 | Engage with opportunities to contribute to relevant policy development within their institution | - The RKEO mailing list, newsletter and increased online presence will make managers of researchers aware of their various opportunities to contribute to relevant policy. We hope that this will lead to an increase in those beginning to do so alongside manager representation on working groups and Research Committee. | - Monitoring and an annual review of committee and working group membership to ensure research managers from all colleges have a fair opportunity to contribute to relevant policy. - At least 55% of researcher plus respondents to CEDARS who manage research staff to state that the institution values their contribution to policy relevant to researchers (question 15.7) | Upon completion of third CEDARS | RKEO | This is a new action for 2020. Welcoming staff to contribute to policy and highlighting the processes for doing so will be a gradual process, hence the longer term deadline here. | - The CEDARS question referenced here is no longer a part of the survey. - Our work in this area is best reflected in our approach to consultation workshops with researchers, for instance around the next research assessment exercise, or around UKRI's recent draft EDI strategy. This approach has been strengthened by stronger relationships between the RDWG and the Readers' and Professors' representatives. - This action will be carried forward to our new plan | New
Researchers must:
ER1 | Ensure that they work in accordance with institutional policies, procedures and employment legislation, as well as the requirements of their funder | - The mandatory online training completed by staff when they join the University covers this information but the importance of adherence to it will be compounded by stronger relationships between the RKEO and researchers. - We will make sure that ECRs develop stronger relationships with Research Development Partners in the RKEO through information in the supplementary induction pack and through adequate guidance on the funding support available through the RDP. | - At least 50 research staff to attend/access an online recording of the, 'Introduction to the Research Funding Landscape and Searching for Funding' workshop throughout the year. This workshop will be offered three times. | 2021-07-01 | RKEO | This is a new action for 2020. | - This workshop has stopped running since the development of our RD Hub, which is home to a selection of videos and guides focussed on the funding landscape. - Mandatory HR training continues to raise awareness of policies, procedures and legislation. - Relationships between ECRs and RDPs continued to be strengthened this year through our RKEO Grant Writing Group, which covered topics from the funding landscape, to data management, collaboration with business, impact and writing a case for support. Recordings of presentations from this group can be found on our RD Hub and Youtube. - 21 attendees were at Intro to Funding our "Funding Landscape" playlist on Youtube has over 100 views. "Searching for Funding" did not go ahead, although we had 17 attend a workshop outlining how to use Research Professional to search for/identify funding. - This action is complete | New
ER2 | Understand their reporting obligations and responsibilities | - Include Data Management training and support from newly recruited Data Management Officer in RKEO into the RDP - Include a session on Data Information Governance in the new RDP | - Have at least 35 attendees (researcher plus) at our generic Data Management training event annually, which will be run twice. | 2021-07-01 | RKEO | This is a new action for 2020. | - This workshop will not run in 2021/2 and was replaced by online materials and incorporation in our Grant Writing Group Programme. 23 attended in 2020/1 however. - The new Res Dev Hub includes new video and written resources for development around RDM and encourages staff to get in touch with the University's RDM Officer - Next year, we will be offering school level provision to those SRLs who want the support, and an introduction to reporting (of research data RE for HEBCI, and the importance of keeping one's data up to date), as well as to data management, will be involved in this. - This action will be carried forward, in part, to our new action plan | New
ER3 | Positively engage with performance management discussions and reviews with their managers | - Improve the support in place for career progression internally and externally through ensuring comprehensive delineation of university promotion policies and processes at local inductions and through information stored in a researcher specific online space. - HR to provide appropriate training to allow managers of researchers to carry out these reviews effectively. The new processes will be advertised to researchers through the RKEO mailing list and blog as well as through the traditional channels. | - 50% of research-only staff responding to CEDARS to state that they found their most recent performance review useful (question 20.a) | Upon completion of the third CEDARS. | RKEO, HR | This is a new action for 2020. The support outlined here, again, is taking a new form and will take time to embed itself into the research staff journey at Westminster, hence the longer term deadline. | - 63% of respondents agreed that their last appraisal was useful. - The RDWG continues to push for more clarity on progression pathways for research staff and is involved in ongoing discussions with HR and OD around how best to implement changes once they have been agreed. - This action is complete | P5.6
ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community | - We will present researchers with this opportunity to act accordingly through Research Community events and encouraging cross college/school networking. Such opportunities should be broadcast through our new RKEO newsletter. | - 60% of all CEDARS respondents claiming to feel valued by UoW for their contributions to grant/funding applications (question 14.1). | Upon completion of the second CEDARS | RKEO, Research Communities, | This is a new action for 2020. | - Only 43% of respondents in the second CEDARS responded positively to this question. - This success measure was perhaps not entirely appropriate for the obligation in question and a better measure going forward could be the number of colleagues from different areas of the university attending community events and consultation workshops. - This action will be carried forward to our new action plan | P5.2
Professional and Career Development
Institutions must:
PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors | - Design and implement a comprehensive programme of training and development for researchers shaped by the Vitae RDF, running through the academic year. This training will be available for both research-only staff and academic and research staff. | - Retention of research-only attendees through the RDP's first year (50% of research-only staff attendees to have been to at least two events per term) | 2021-07-01 | RKEO | This is, in part, carried over from an action outlined in row 41 of our 2016 Action Plan (as below): Provide a programme of training and development opportunities around the concept of ‘the digital researcher’ and from another outlined in row 31 (as below): Develop a central programme of career development activities for researcher staff and appropriate local faculty activities as need and provide career advice for researchers | - The metric in the proposed success measure is perhaps not as useful as the total number of attendees. There were 203 researcher-plus colleagues at workshops in 2020/1 and over 220 from September 2021 to June 2022. - Our efforts with hybrid training sessions, programmes for ECRs and more consultation with a broader range of researchers, as well as more discipline specific workshop offerings are all in pursuit of there being opportunities for 10 days CPD per year at Westminster. - The RDWG continues to monitor and report on engagement with the RDP to inform the planning of future provision. - This action will, in part, be carried forward to our new action plan | P3.1 P3.3 P5.5
PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers | - Monitor the success of new career development review discussion policies from UEB and HR through CEDARS. | - Include researcher feedback on this issue obtained through the first two CEDARS in RDWG annual report to Research Committee. | Upon completion of the second CEDARS | RKEO, UEB, HR | This is a new action for 2020. | - The RDWG continues to monitor the success of new initiatives. - Researcher feedback on this through CEDARS was fed into our annual report to Research Committee. - This action is complete | P3.10
PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers | - With a focus on ECR development, the RDP will provide an introduction to the research funding, publishing and knowledge exchange landscapes in order to familiarise research staff with the career opportnuities available to them. | - 50% of all respondents to CEDARS agreeing that the University supports them in their broader career aspirations. | Upon completion of the third CEDARS. | RKEO | This is carried over, in part from an action outlined in row 30 of our 2016 Action Plan (as below): Design a series of career development workshops for researchers to include preparation and writing CVs & personal statements, interviewing skills. The RDP is a new way for the University to address researcher development in 2020/1. The programme will adapt and expand each year, taking on career management and advice with more weight of intent over time. As it is not at the core of the programme in this first year, this action requires a longer term deadline. | - 42% in the second CEDARS agreed that the University supports them in their broader career aspirations. - To achieve this target by the third survey, we will continue to intenally promote Vitae materials on career management as well as looking into coaching initiatives for research-only staff to supplement their engagement in the researcher development programme. - This action will be carried forward to our new action plan | P3.1
PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills | - Clearer placement of University and College WAM policies and procedures as well as clearer explanations through local inductions and through use of a researcher specific online space. - Researchers must all be given the opportunity to engage in ten days of CPD per year. | - An annual increase in attendance at RDP events as the programme grows. - 80% of researcher plus CEDARS respondents to say that the University treats them fairly with regards to CPD. | Upon completion of the second CEDARS. | RKEO | This is a new action for 2020. | - 77.8% felt fairly treated regarding CPD, marginally shy of our target. - Efforts to support the growth of research identities at UoW have been helped by the introduction of our Researcher Development Awards, which seek to support future leaders over two years with a small pot of money and termly targeted support from the RKEO, as well as a mentor. - This action is complete | P3.11 P3.14
PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this | - Introduce the topic of working across employment sectors to the researcher mentoring circles initiative's list of themes. Monitor and evaluate the impact of these conversations. | - Continue to monitor and evaluate researchers' understanding of working across sectors | 2022-07-01 | RKEO | This is a new action for 2020. | - The RKEO has expanded from a small team of less than ten, to over twenty in the last two years, and now has expertise in collaboration with business. This Collaboration team within the office will feed into future support with moving between and working across sectors. - The RDWG continues to monitor this through the CEDARS, through other surveys and through workshop feedback. - This actional will be carried forward to our new plan | P3.2 P3.4
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities, and researcher career development reviews | - The RDWG will report to Research Committee (and our 'Concordat Champion' - PVC Research - will then report to UEB) with an annual review of the group's progress. - The researcher specific online space mentioned elsewhere in this document will serve not only as a storage space for policy and useful training information, but an online forum for communication and feeding back on the support researchers feel they need. - Monitor attendance at all RDP events | - Submission of an annual report to PVC research and Research Committee. - An increase, year on year, in total attendance of RDP events. | 2022-07-01 | RKEO, RDWG, Concordat Champion | This is carried over, in part from a previous action, set out in row 35 of our 2016 Action Plan (as below): Continue to evaluate implementation of the Concordat in terms of policies and training offered and also in row 33 (as below): HRERA Steering Group will report to the University HR Committee who in turn report to the Court of Governors. Formally review the progress of the Action Plan each academic term and at the end of Year 1 and Year 2 | - We project that attendances will increase this year to last, and increase further next year with the integration of school specific workshops, after this year's pilot. - We have submitted an annual report to Research Committee (June) including an outline of attendances at workshops for the last two years. - We continue to monitor attendance, feedback and engagement at all workshops. Looking forward, this monitoring must be extended to our online environments, namely the youtube, RD Hub and prospective platforms for hybrid training. - This action will be carried forward to our new plan. | New
Funders must:
PCDF1 | Incorporate specific professional development requirements in relevant funding calls, terms and conditions, grant reporting, and policies. This should include researchers' engagement in a minimum of 10 days' professional development pro rata per year, and evidence of effective career development planning | x | x | x | x | x | x | P3.7 P3.9
PCDF2 | Embed the Concordat Principles and researcher development into research assessment strategies and processes | x | x | x | x | x | x | New
PCDF3 | Acknowledge that a large proportion of the researchers they fund will move on to careers beyond academia, and consider how they can encourage and support this within their remit | x | x | x | x | x | x | New
Managers of researchers must:
PCDM1 | Engage in regular career development discussions with their researchers, including holding a career development review at least annually | - HR will offer appropriate training in giving career development discussions in line with the new appraisals policy. - The Research Team Leadership being facilitated by Advance HE at the University for two days as part of the RDP will also improve managers' confidence in holding these conversations. | - 70% of researcher plus respondents to CEDARS to describe career development reviews with their manager as useful (question 30) | Upon completion of the third CEDARS. | RKEO, HR | This is a new action for 2020. Again, the University's process for research staff appraisals is currently being reconstituted and it will take time for the results of these changes to become clear. | - 56% of colleagues described their most recent career development review as useful. - To meet our target of this figure reaching 70% by the third CEDARS, we are seeking to improve our support for research specific mentoring and to incorporate the researcher perspective more clearly in higher level HR career development guidance. - The creation of our Researcher Development Hub is, in part, in service of this aim, as it provides more resoruces for managers to point colleagues towards, and more information and opportunities for researchers to bring up with their managers. - The RKEO is seeking to improve its support for research mentoring through growing relationships with School Research Leads and through the Researcher Development Award initiaitve. - This action will be carried forward to our new plan. | P2.3
PCDM2 | Support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments | - Monitor and evaluate researcher experiences in preparing for a diversity of careers through CEDARS, feedback forms from relevant RDP events and through a feedback form on a researcher specific online space. - Continue and expand our researcher mentoring circles initiative outlined elsewhere in this action plan and in our accompanying four year report. | - 60% of researcher plus respondents to CEDARS to agree in question 22.5 that the University supports them in their broader career aspirations. | Upon completion of the third CEDARS. | RKEO | This is carried over, in part, from a previous action in row 37 of our 2016 Action Plan (as below): Design/write a mentoring policy and guidelines to incorporate mentoring for research staff See cell G68. | - Due to the small number of contract researchers at the institution, this goal presents a significant challenge for the unviersity. - Only 42% of CEDARS respondents felt supported in their broader career aspirations in the last survey. - The new Researcher Development Awards scheme seeks to give time and space to researchers to consider their broader aspirations, and support through mentoring and termly workshop meetings to explore opportunities. - Further to this, the E-MCR blackboard page provides a new space for researchers to share experiences and responses to barriers faced around this - This action will be carried forwrd to our new plan. | P3.4 P3.8 P5.5
PCDM3 | Allocate a minimum of 10 days pro rata, per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development | - The RKEO will publish a new RDP handbook at the beginning of each academic year and managers of researchers will all receive instruction in encouraging the researchers they manage to attend as many relevant events as possible. - Monitor and evaluate how to properly measure this target of 10 days (CPD) through consultation with researchers attending RDP events and through feedback from managers of researchers holding the new appraisals conversations. | - 50% of researcher plus respondents to CEDARS Q.34 to have engaged in at least 5 days of CPD in the past year (5 days as self-defined by the researcher) | Upon completion of the third CEDARS. | RKEO | This is a new action for 2020. See cell G68. | - Only 29% of respondents had engaged in at least 5 days CPD in the last year in the last CEDARS. - Our initial target may well have been slightly ambitious, but there is also an issue here around how colleagues define CPD and whether they are maintaining a record of their engagement with their professional development. The RKEO will offer more support in maintaining a CPD record going forward. - The growing number of resources on our RD Hub, as well as workshops encouraging engagement with the Vitae RDF (for instance through the RD Awards programme) seek to raise awareness of researcher development internally, strengthen colleagues' understanding of what CPD can mean as a researcher and provide opportunities to engage in more CPD activites. - This action will be carried forward to our new plan | New
PCDM4 | Identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours | - Improve the channels of communication between researcher, manager of researcher and RKEO so that issues are resolved promptly and the adequate support is provided for researchers as often as possible. This will happen through our previously outlined development of the office's online presence and a clear delineation of policy, procedures and responsibilities for various areas of support on a researcher specific online space. | - 70% of research-only staff responding to CEDARS to say that they feel their manager supports them to develop their research identity. | Upon completion of the third CEDARS. | RKEO | This is a new action for 2020. The channels of communication outlined here take time to establish and take hold in the researcher development journey, hence the longer term deadline. | - We have strengthened the channels of communication between researchers and the RKEO over the last two years through the expansion of our office and more targeted meetings and relationship building with leading researchers in each school. This has included involving research staff in events, workshops and consultations. - 43% of respondents felt that their manager supports them in developing a research identity in the last CEDARS, which is significantly below our target. Our target may have been slightly overambitious, but we hope that the already mentioned improvements to our PDR process for researchers will support growth in this area. - This action will be carried forward to our new plan | P3.6 P3.9 P5.5
PCDM5 | Engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development | - The RKEO will highlight specific sessions in the RDP aimed at managers of researchers in an effort to engage them in leadership and management training. - Offer the two day Research Team Leadership training programme facilitated by Advance HE for emerging managers of researchers. | - 80% of managers of research-only staff responding in CEDARS that they feel comfortable providing effective feedback to those that they line manage. | Upon completion of the third CEDARS | RKEO | This is carried over, in part, from a previous action outlined in row 34 of our 2016 Action Plan (as below): Deliver an annual leadership training programme for academic leaders and managers across the University, designed and run in-house to enhance leadership and line management skills for Academic leaders See cell G68. | - 90% of managers of research-only staff felt comfortable providing effective feedback in the last CEDARS, which exceeds our target. - This action is complete | New
Researchers must:
PCDR1 | Take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year | - The RKEO will encourage attendance at RDP events through promoting guest academic speakers, filtering of information through school research leads, through our mailing list and blog and through the University-wide weekly newsletter. A quarter of the 2020/1 RDP will be sessions under the theme of, 'Taking Charge of Your Career'. | - 50% of research-only respondents to CEDARS to have undertaken at least 10 days of CPD in the past year. | Upon completion of the third CEDARS. | RKEO | This is a new action for 2020. This action relies on the growth of the new RDP, on an increased response rate to CEDARS and an increased understanding of how to define CPD to come out of the RDP sessions and a new researcher specific online space; these changes will be gradual and thus, the deadline is slightly longer term here. | - 19% of research-only colleagues responding to the second CEDARS had undertaken at least 10 days CPD in the last year. - We hope to see this number increase with the growth of our researcher development programme and improved provision for managers of researchers to advise on CPD, but this target may have been overambitious. We will look to adjust the success measure here in our forward facing action plan. - This action will be carried forward to our new plan | P5.5
PCDR2 | Explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments | - Explore the possibility of continuing the FUNDamentals series as an opportunity for career progression advice from colleagues at other institutions and from funders. (The FUNDamentals series is an attempt to bring together similar post-1992 institutions in London for events with key speakers from funding bodies aimed to inform and also enable networking - http://blog.westminster.ac.uk/researchoffice/fundamental-cafe-british-academy/). - Continue and expand our researcher mentoring circles initiative. | - Explore the possibility of re-imagining and resuming the FUNDamentals series. Make a decision by 2021/2 - Continue the researcher mentoring circles initiative. | 2021/2 | RKEO | This is a new action for 2020. | - The success measueres and action here perhaps don't fit the Concordat principle as well as they should. - We have published our research FUNDamentals guidance on the RD Hub and they have been engaged with well, especially by new staff. - The mentoring circles initiative has been continued and mentoring further focussed on through our support for recipients of the inaugural Researcher Development Awards. - To better meet the objective of the Concordat principle here, our actions should focus more on mentoring and training, which we will do in our new forward facing action plan. - This action is closed | P3.8
PCDR3 | Maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications | - As mentioned elsewhere in this document, a uniform University policy on PCD plans and portfolios are being put together at present by UEB and HR. Once the policy is finalised, HR will provide appropriate training and the RKEO will ensure that all managers of researchers are aware of their responsibilities in order to ensure that all researchers are maintaining up-to-date plans. | - 55% of all CEDARS respondents to state that they have a clear career development plan (question 29.5) | Upon completion of the third CEDARS. | RKEO | This is a new action for 2020. As this action centres around re-imagined processes and their effects over time, there is a slightly longer term deadline here. | - 39% of respondents in the last CEDARS stated that they maintain a career development plan. - We intend to improve this figure by extending our RD Programme into more school level sessions and highlighting the importance of considering career development where appropriate, and keeping track of it - This action will be carried forward to our new action plan. | P5.5
PCDR4 | Positively engage in career development reviews with their managers | - Monitor and evaluate the engagement of research-only staff with career development reviews. | - A community of researchers engaged with the University's new appraisal processes. At least 90% of researcher plus staff to have had an appraisal in the last two years. | Upon completion of the third CEDARS. | RKEO | This is a new action for 2020. The promising updates to our career development review process for researchers will take time to demonstrate positive results, hence the slightly longer term deadline here. | - 77% in the second CEDARS had an appraisal in the last two years. We expect this figure to rise to closer to 100% by the next CEDARS after the implementation of our improved PDR process and more work towards strengthening research culture in each school (we have recently appoint College Research & Knowledge Exchange Directors, who replaced Research Directors in each College, and are also working to appoint a KE lead in each school, working towards a joined up approach to our support for R&KE). - This action will be carried forward to our new action plan. | P3.10
PCDR5 | Seek out, and engage with, opportunities to develop their research identity and broader leadership skills | - The new RKEO newsletter will highlight these opportunities to researchers. Managers of researchers will encourage engagement through direct dissemination of opportunities where appropriate. | - 50% of all respondents to CEDARS agreeing that their line manager supports them in working towards promotion opportunities. | Upon completion of the second CEDARS. | RKEO, HR | This is a new action for 2020. | - 36.5% felt that their manager supports them in working towards promotion opportunities. - To improve this figure, we have included promotion information and guidance in our new E-MCR network BB page and are looking to design workshops around promotion to Reader/Professor in the next two years, as well as providing a bank of example applications. - The CEDARS question asking about managers' support for building a research identity may be a more useful statistic, and we will incorporate this into our forward-facing action plan. - This action will be carried forward to our new plan | P5.5
PCDR6 | Consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation | - Introduce workshops to the RDP which include information on the University's support structures for KE. | - Have two sessions in the RDP which include presenters from the Knowledge Exchange team. | 2022/3 | RKEO | This is a new action for 2020. | - Two workshops were run this year, facilitated by our new Collaborations Team, attended by 28 colleagues. - We intend to expand this going forward with a blog series on collaboration, followed by more workshops next year and school level sessions looking at ways of collaborating with business. - This action is complete | P5.2
* The Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional suport staff; technicians.

## Acronyms and Links
CEDARS | Culture, Employment and Development in Academic Research Survey
CPD | Career and Professional Development
CRD | College Research Director
CREC | College Research Ethics Committee
CROS | Careers in Research Online Survey
DRDP | Doctoral Researcher Development Programme
E&C | Environment and Culture
E/M-CR | Early/mid-career researcher(s)
EDI | Equality, Diversity and Inclusion
FRD | Faculty Research Director (We now have CRDs)
FREC | Faculty Research Ethics Committee (We now have CRECs)
HOD | Head of Department
HOS | Head of School
HR | Human Resources
HRERA | Human Resources Excellence in Research Award
HRM | Human Resource Management
HROD | Human Resources and Organisational Development
KE | Knowledge Exchange
LMS | Learning Management System
LOD | Learning and Organisational Development
MI | Management Information
OD | Organisational Development
PI | Principal Investigator
PIRLS | Principal Investigators and Research Leaders Survey
PPCD | Personal and Professional Career Development
PDR | Personal Development Review
PDF | Personal Development Framework
RDF | Vitae Researcher Development Framework
RDP | Researcher Development Programme (This programme is to be available both to research-only staff and those on academic and research contracts)
RDWG | Researcher Development Working Group
REC | Race Equality Charter
RKEO | Research and Knowledge Exchange Office
SES | Student Experience Survey
SLD | Staff Learning and Development
SRL | School Research Lead
TNA | Training Needs Analysis
ToR | Terms of Reference
UEB | University Executive Board
UoW | University of Westminster
UREC | University Research Ethics Committee
WAM | Workload Allocation Model
Researcher Development Hub | https://blog.westminster.ac.uk/researchoffice/researcher-development-hub/
R&KE Office Blog | https://blog.westminster.ac.uk/researchoffice/
R&KE Ethics and Integrity Webpages | https://www.westminster.ac.uk/research/research-and-knowledge-exchange-governance
R&KE Office Youtube Channel | https://www.youtube.com/channel/UCKQ2lMy0iHe9FIpVHid5Wwg